## List1
| Scope of the question: | General questions: | [27 empty] | System availability questions: |  |  | Control room questions:
| Question: | What approximate costs do you expect for the implementation of the Traffic Management System (‘TMS’) for high-speed lines in the Czech Republic, including hardware, software, integration with existing systems, staff training and other related activities? Please indicate the range of these costs and factors that may affect their amount. | Do you agree with the proposed schedule (Appendix 4) for the TMS project implementation, including the deadlines for completing individual milestones? If not, please provide comments and suggestions for schedule modifications that, in your opinion, would better reflect the realistic possibilities and optimal procedures for TMS implementation. Furthermore, please indicate whether you are able to suggest an approximate percentage distribution of the total project amount across individual milestones? | Based on your experience with similar projects, we would like to ask you to submit an indicative schedule for the implementation of our project. This schedule should include the milestones from Appendix 4. In addition to these milestones, we are also interested in other significant milestones that you consider key to the successful completion of the project. We are particularly interested in the estimated duration of individual stages and the dependencies between them. | Do you agree with the architecture shown in Figure 3 Procurement: TMS Control Level for HSL (Appendix 2)? If not, do you propose another more suitable option for building the TMS Control Level? At the same time, do you see any potential limitations or problems in the proposed architecture that could affect the functionality of TMS? | With reference to the architecture shown in Figure 3 Procurement: TMS Control Level for HSL (Appendix 2), please specify which subsystems from this figure are part of your TMS solution and will be delivered as part of this procurement. Please also indicate whether your solution includes other subsystems that are not shown in this figure, and if so, which ones specifically. | What technical solutions do you propose for building the interface between the TMS and future signalling systems from various manufacturers, what standards and protocols would you recommend to ensure smooth communication and data exchange between these systems? | What is your approach to adapting the EULYNX SCI-CC specification for the Správa železnic / HSL environment and what are your proposals for using the interface within this project? | With regard to the division of the Správa železnic architecture according to Figure 2 (HSL automatic operation concept, Appendix 2), it is necessary to define a communication protocol between the TMS Control Level and the Executive Level (RBC, interlocking) for high-speed lines. Are you able to define this protocol in cooperation with Správa železnic and with regard to the first HSL launch date? Does your company have the necessary competence to develop this protocol? If you believe that defining this communication protocol is not necessary, what alternative do you propose? | Alternatively, how will you ensure that the system you deliver to us is open for integration with signalling systems from various suppliers? What specific steps will you take to ensure that the TMS will be compatible with different types of signalling systems and allow us to easily connect new HSL sections to the TMS, regardless of the signalling system manufacturer? | Do you guarantee the compatibility of your system with at least three different signalling system suppliers without the need to use EULYNX-type solutions? If so, please list the specific names of all manufacturers whose signalling systems your TMS system is compatible with. | If we were to require complete TMS development, what is your estimated timeframe for the development and implementation of the TMS solution, including all necessary modifications and integrations? | If you were to recommend a ready-made solution (without development), how could it be adapted to our requirements? | Regarding paragraph 3. Minimum requirements for TMS (Appendix 2, page 4): Do you have any difficulties implementing any of these requirements, do you consider them difficult to meet, or do you have any feedback on them? | Will the entire final product be delivered by a single contractor as part of the project implementation, or will it contain components or parts from other suppliers? If the product will contain parts from multiple suppliers, please specify which parts will be developed/delivered internally and which externally. | Do you have experience with implementing TWS (Track Warning System) level SCWS (Signal Controlled Warning System) on an operating railway infrastructure (line section) in the EU or in non-EU countries? | What experience do you have with similar contracts and specifically which contracts have you worked on over the past 7 years? Given the nature of the contract, is a 7-year period acceptable to you for assessing your experience or would you recommend considering a different period? | Is it possible to supplement your TMS with SCWS-I, or what are the limiting conditions of the system? | How do you estimate the financial and time requirements for connecting another HSL section to an already functioning TMS system? Does the format of data provided for implementing another section have an impact on this? Do you prefer any data format? | Is it possible to connect your TMS with a TMS from another manufacturer, if it were appropriate for a certain cross-border HSL connection? | As part of the requirements for long-term sustainability and flexibility of the TMS solution, what is your approach to providing the system source codes? Are you open to discussing the terms and scope of providing or potentially selling the source codes, and what are your potential concerns or conditions associated with this aspect? | In addition to providing the source code itself, what specific steps are you willing to take to ensure the transfer of ownership rights to this code, so that we have full control over its further possible development and modifications? Is this a feasible requirement for your company? | What support and system development period would you anticipate being included in the contract? | What factors do you think determine the lifetime of the system (technical, moral) and what is your experience with long-term support for similar systems? | What exit strategy do you propose? In the event that the supplier would not be able to continue fulfilling the terms of the service contract or in the event of termination of system support, what mechanisms for transferring the management and operation of the system do you propose? How would the continuation of operation without a negative impact on the system be ensured? | What technical solutions do you propose for building the interface between the TMS system and future communication systems from various manufacturers (operation applications, CCTV systems, information systems, etc.), what standards and protocols would you recommend to ensure smooth communication and data exchange between these systems? | Requirements for ensuring the cyber security of ICT Infrastructure, cable routes and facilities (technological rooms and server rooms), including distribution cabinets in which supporting assets are operated and used, must comply with the Cyber Security Act (Act No. 181/2014 Coll.) and the Cyber Security Decree (Decree No. 82/2018 Coll.), which implement the relevant EU regulations (Directive (EU) 2022/2555 of the European Parliament and of the Council of 14 December 2022 concerning measures for a high common level of security of network and information systems across the Union and Regulation (EU) 2019/881 of the European Parliament and of the Council of 17 April 2019 on ENISA and on information and communications technology cybersecurity certification and repealing Regulation (EU) No 526/2013). Are you able to meet the requirements of these legal regulations with your solution? | From your perspective, is it feasible for the proposed system to support access control by connecting to Active Directory and at the same time secure communication using an SSL certificate issued by an internal certification authority (CA) with the ECDSA algorithm? If any of these parts is not feasible, please state the reason and propose an alternative if possible. | From your perspective, is it feasible to require that the proposed system, specifically its ability to connect to a central system for collecting logs (currently SPLUNK), is ensured? If this requirement is not feasible, please state the reason and, if an alternative exists, indicate whether it is possible. | Can you generally describe how you ensure high availability of the TMS system? What do you consider to be a suitable/achievable/necessary value for TMS system availability? Please also provide a specific value for system availability during HSL operation. | In the event of a system failure at one workplace, the system must allow immediate takeover of activities by another workplace, i.e. between workplaces in Prague and Přerov. What solution do you propose to ensure immediate workplace takeover in the event of a failure? | What solution do you use to ensure the fault tolerance of the system? | Are you able to design and implement traffic control rooms that will be fully compatible with our Traffic Management Concept (Appendix 3) and our functional requirements? Are you able to fulfil these requirements in full? | Based on your experience with building traffic control workplaces for other high-speed lines, we would like to know your opinion on the proposed division of workplaces in CDP Praha (TCC Prague) and CDP Přerov (TCC Přerov). With regard to the HSL Section Description Tables (Appendix 5), we are interested in whether this arrangement is suitable in your opinion in terms of the efficiency of the controllers' work and smoothness of operation, or whether you would recommend any adjustments. | Efficiency of workplace division: What is your view on the current structure of control positions, including the distribution of line, traffic and electrical control workplaces? Does this division correspond, based on your experience, to proven models for other high-speed lines? | Smoothness of traffic management: Do you believe that the current division of sections between individual CDPs (TCCs) is suitable for ensuring the smoothness of operation on the controlled lines? Where and what possible optimisation opportunities do you see for the proposed solution? | Is the currently proposed staffing of workplaces for HSL control sufficient to ensure all necessary activities, or is there a lack of personnel in some areas of activities? If you see any alternative arrangement options that might be more suitable for HSL control, please indicate them. | Do you consider the questions from chapters: 1, 2, 3 sufficient to understand our intention and the future procurement? If not, what essential requirements should be clearly defined in the future procurement from your perspective? Would you recommend another form of consultation to clarify the procurement?
|  | Question 1 | Question 2 | Question 3 | Question 4 | Question 5 | Question 6 | Question 7 | Question 8 | Question 9 | Question 10 | Question 11 | Question 12 | Question 13 | Question 14 | Question 15 | Question 16 | Question 17 | Question 18 | Question 19 | Question 20 | Question 21 | Question 22 | Question 23 | Question 24 | Question 25 | Question 26 | Question 27 | Question 28 | Question 29 | Question 30 | Question 31 | Question 32 | Question 33 | Question 34a | Question 34b | Question 35 | Question 36
1 | XXX | Based on the basic requirements and the information currently available regarding the known requirements, integrations, and topology, the estimated cost range for the implementation of the Traffic Management System (TMS) for high-speed lines in the Czech Republic is between 11.5 million and 13.5 million EUR (CAPEX). Some factors may affect these costs are: Operational uncertainties Dependencies on external suppliers (e.g., interlocking systems) Uncertainties in projects on which the TMS depends (e.g., signaling, SCADA, communications) | Milestone 1: Achievable. It is desirable to include internal sub-milestones: Some processes are set up to ensure the project success: correct requirement management, documentation management, human factors management and stakeholders’ group establishment. Preliminary design (6 months from the signing of contract) Architecture design including interfaces with external systems (8 months from the signing of contract) Prototype to analyse project customisations (12 months from the signing of contract) Milestone 2: Achievable. Milestone 3: Achievable. There are assumptions to set up this milestone: All external systems are ready to be tested and deployed accordingly to the design. All data configuration is set and stable. Milestone 4: Achievable. Milestone 5: Achievable. There are assumptions to set up this milestone: Preventive maintenance is included in the maintenance operation. A SLA has been set up to fix any possible bug or error during the operation. Milestone 6: Achievable. Milestone 7: Achievable. | Added milestones: Design and specification, Safety certification | Missing interfaces: Interface TMS - FRMCS (voice concentrator) Interface TMS - Passenger Information System (PIS) Integration with Power BI Integration with Centralised Detector Control (CDC) Limits: Signalling deadlines can impact on the TMS delivery CONOPS with the desired future operation can impact in TMS design Data stability can impact in TMS configuration, tests and delivery | Modules of the solution found in the requirements: SIM: Simulation of interlocking, Simulation of trains TMM: Forecast, delay and conflict calculation, Plan/replan capabilities, Delay justification, Temporary speed management, Possession management, Train management, Train consist management CTC: Signal monitoring and control, Train tracking, Train describer ARS/ANS: Automatic route / headcode setting CSS: Alarm / alert management, User management, Configuration, Control area management, Rolling stock management SCADA: Integration with energy scada PCE: Integration with RBC PAM: Reporting, Playback Zabbix: System monitoring and log, Modules not found in the requirement TPS: Timetable generation PIS: Passenger information system Videowall: Visualisation CDC: Integration with Centralised Detector Control | Communication between CTC – Interlocking: there is an adapter module called FEC (FrontEnd of Communications) in charge of translate native interlocking protocol (whenever no Eulynx available) to the CTC. This decouples the logic of translation from the CTC and ease the replacement of this module when the interlocking is replaced or to integrate interlockings from disparate suppliers with own protocols. EULYNX SCI-CC is the recommendation for the interface with future signalling systems even though Our company TMS has been integrated with all the proprietary protocols so far. See table on question 10. | The approach is to implement all mandatory elements of the EULYNX SCI-CC protocol and analyse the optional ones, including the extra parameters and objects required by the specific signalling layer of the project. One of the main points is to agree the publish IDs for all the elements and the command catalogue for each interlocking. | Yes, we have defined and implemented this protocol before in other projects, using the EULYNX SCI-CC. That protocol includes the set up and monitoring of temporary speed limitations and emergency stops at least. | As indicated in question 6 we provide an intermediate layer to decouple the CTC functionality with the interlocking protocol. That way, this integration layer provides a unified command and control view from all the interlocking, regardless the technology and supplier. One example of this strategy is our TMS for Lithuanian Railways, where we integrated 6 different protocols from disparate suppliers. One major achievement in this project was the replacement of interlocking from one technology (NEVA) without any impact in the operation. The steps to achieve this are: - The set up of the single model and protocol for the CTC that include all the singularities from all the interlocking types. - Receive the information of the supplier protocol of communication and data layer. - Creation of specific FECs (adaptation modules) with responsibilities of: o Translation between the native interlocking protocol to the CTC protocol. o Translation between the native interlocking model to the CTC model. o Transformations needed to keep the homogeneous behaviour of the CTC among the interlockings. - Make internal tests with the interlocking supplier connecting laboratories before official testing phase. This ensures the smooth integration and eliminates tunning problems of the protocol adaptation. - Make SIT (Site Integration Tests) testing all the element types and possible status. Then testing a % of elements for each station. This ensures correctness on the configuration data. - Document management between stakeholders. Anytime there is a change in the supplier’s side there is a process to update all systems and proceed with tests to ensure correctness. | We have integrated successfully all the interlocking protocols from other suppliers in our projects, as indicated in the following table: <specific examples kept for internal purposes> | Regarding the timeline proposed, 24 months including pre-SAT testing. | Our company TMS has a flexible configuration that can achieve user requirements without development in some areas. The model and processes shall be aligned with Our company’s TMS to avoid developments: • ARS: automatic routing configuring trigger points and route conditions is possible to manage by the user. • Videographic representation of the CTC: SVG files to represent the track elements and status that can be edited with any graphic design tool. • Rolling stock catalogue management: our TMS includes the function to manage it. • User management: our TMS includes the function to manage users, privileges and roles. • Sectorisation: control areas management is part of the TMS functionality. • Graphical timetables configuration: this is part of the functionality of the TMS. • Alarm and alert catalogue and configuration: this can be configured without development. • Language translations of the user interface: this can be configured without development. • User interface workspaces are set up and managed by the user. | All the requirements are totally feasible. Some of them shall require clarification: - When it is mentioned “optimisation of timetables” we need to understand with KPIs to be optimised and whether only in real as we understand there is no timetable generation module (planning). - We need to clarify what type of information we Will receive for sections with “ETCS Level 2 with hybrid train detection”. - Although it is said that “No risk functions are set up within the TMS control from the traffic control centre (CDP)” we assumed a Safety analysis shall be performed. - We will need clarification about ATO protocols to be implemented - We will need clarification about FRMCS implementation. - We will need to clarify the timetable generation system integration or process. - Regarding the redundancy mentioned for the TMS Control Level solution: o It is assumed that communications between the data centres where the TMS Server solution will be deployed (located in Prague and Přerov) are out the scope of the proposal, being the responsibility of the Client. We need confirmation about this connection (latency, bandwidth, network extension possibilities) o We need to confirm if it is feasible to have a third site to study different possibilities of geographic high availability of the TMS solution. o Due to the distance between both centres, Prague and Přerov, which directly affects the communication between them, and therefore the geographic high availability solution, is it valid to propose an active-standby solution between centres with manual failover, providing a RPO that tends to 0 and reducing switching times? o We need to confirm whether it is required that the IT platform be an exact replica in both sites (Prague and Přerov) or if, on the contrary, it is valid to configure one of the datacentres as Disaster Recovery, allowing to optimize hardware and software resources in this secondary centre, assuming that it would only come into operation temporarily in case of a major failure in the main datacentre. It is assumed that the IT platform will be designed to provide redundancy and high availability locally in each of the data centres at different levels and that a backup solution will also be considered to recover the system to a state prior to a failure if required. o We need to confirm if an Active- standby configuration between datacentres with a manual failover procedure is valid for the proposal. o We need information about expected RPO and RTO for the failover scenario between datacentres in order to evaluate the most appropriate solution for geographical high availability. | • All the Software and Hardware will be delivered by Our company. • Some libraries and components are from external suppliers: o Database  Cassandra  Ignite  PostgreSQL  Elasticsearch o Integration component  ActiveMQ o Monitoring  Zabbix  Grafana o Libraries and frameworks  Springboot  Angular o Containers  Docker  Kubernetes o Operating system • Regarding to the ICT platform o All proposed equipment is based on COTS product from the main brands in the market with proven reliability such as HP or Dell among the main ones. o It is important to mention that Our company's software solution has been designed to be platform and hypervisor agnostic, so our solution can be deployed over any main market-leading suppliers/manufacturers like XXX or YYY and over different virtualization hypervisor, such as Nutanix or VMWare adapting to the last generation technologies. | Regarding Our company´s on-track IoT solutions, we are currently developing our Trustable Warning System. It is a solution that enables a safety zone on the track for Operation –improving safety on Level Crossings -and maintenance work agnostic to the technology on board the railway operator. It is integrated with actuators to warn of the approach of a train to the designated safety zone. The solution inference potential risks for involved actors on the designated safety zone: • Increasing the safety conditions in the area by broadcasting problematic or important information associated to specific points in the route of the vehicles that will allow them to take the necessary actions in advance. • Improving the compatibility with any existing and future communication protocol to support the information exchange between the different actors and offering multiple benefits and progresses to the market. • Ensuring interoperability with previously installed systems in other sectors (apart from the Rail sector) and being compatible with the existing infrastructure. • Providing more scalable architectures, control capabilities to the edge and distributed management. • By means of the proposed solution, zones such as level crossing, road crossing, works zones, etc. could be protected without using traditional cabling systems. | The diversity and complexity of the projects in different countries demonstrate Our company's capability to manage and execute TMS contracts effectively. Please find below an overview of some of Our company´s TMS main refence projects: <kept anonymous> | Understanding that you are referring to SCWS integration, it is an area in which we are currently working on. As of now, it is not integrated. | This estimation depends on: - Kilometres of the new section - Interlockings and track elements of the new section - Number of trains crossing sections - Number of workstations to operate the new section - Whether are new systems to be integrated in the TMS - Number of concurrent users to access all the functionalities. A digital data format is provided, but the specific format is not relevant as the data is frozen in the time to configure and test the new section in the TMS. | Yes, it is possible to integrate with another TMS of other supplier. • TAF TAP TSI for regulation • Signalling information and train number exchange | Our company's usual model is to provide our products with a perpetual license. However, as a flexible Our company, we are open to negotiating other approaches that the client may find of interest. In the case of providing the source code, Our company is open to discussing an economic agreement. Our concerns regarding the provision of the source code include ensuring that it is done under a confidentiality agreement and that other companies in the sector do not gain access to this code. Our company includes escrow agreements in its contracts, ensuring access to the source code in case any circumstances prevent Our company from providing the agreed service. All custom developments made for this project will be delivered to the client. Our company is, of course, open to discussing co-creation proposals. However, it is important to note that the advantage of Our company maintaining the source code is that we can continue to manage the product roadmap and future evolutions of the system. | In the event of reaching a contractual and economic agreement for the transfer of the source code, Our company is willing to collaborate with the client by conducting workshops and training sessions for the client technicians selected for the development tasks once the transfer has been completed. This approach ensures that the client's team is fully equipped to take over the further development and modifications of the code. This requirement is feasible for our Our company, and we are committed to providing the necessary support to ensure a smooth transition and effective transfer of ownership rights. | System support during go-live phase can be anticipated as 6 months. | Lifetime of the system can be determined by the technology renewal policy, the stability of the operation processes and normative and the future integrations that can limit the current solution. Our company supports customer where solution is deployed with a strong product roadmap that ease the evolution and upgrade of the installed systems, optimising the lifecycle and make that evolution smooth and compatible with the previous versions. | Our company prepares an exit strategy for its projects in accordance with industry best practices to ensure service continuity. In the event that Our company is unable to continue fulfilling the terms of the service contract or if system support is terminated, the core of the system would be protected with an escrow agreement. This ensures that the client has the capability to continue the operation without any negative impact on the system. By having the core system secured in escrow, the client can access the necessary resources to manage and operate the system independently, thereby guaranteeing uninterrupted service. | Always try to follow the European Standards: System Pillars protocols under the ERA (TAF TAP TSI, Sfera, etc), Rail ML, and any open standards that avoid vendor lock in and ease third party integration. | To comply with this cybersecurity framework Our company will implement in collaboration with Client a multi-layered approach to secure the ICT infrastructure, facilities, and supporting assets. 1. Risk Management • Risk Assessment and Treatment: Organizations must conduct a risk assessment of the ICT infrastructure to identify and evaluate potential cybersecurity risks. Based on the assessment, appropriate risk treatment measures must be implemented to mitigate identified threats. • Continuous Risk Monitoring: Ongoing monitoring of risk factors and regular re-assessment of the ICT systems and cybersecurity posture are required to ensure evolving threats are addressed. 2. Security of Physical and Environmental Access • Physical Access Control: Strong physical access controls must be established to prevent unauthorized access to technological rooms, server rooms, and distribution cabinets. This includes access control systems (e.g., badges, biometric systems) and supervision of access points. • Environmental Security: These facilities must be secured against environmental threats, such as fire, water damage, and power outages. This includes the installation of fire suppression systems, humidity and temperature control, and backup power systems (e.g., UPS or generators). 3. Cybersecurity Measures for ICT Systems • Network Security: Strong network security measures must be implemented, such as firewalls, intrusion detection/prevention systems (IDS/IPS), and segmentation of internal networks. • Secure Communication: Encrypted communication channels for transferring sensitive data between systems must be used to ensure data confidentiality and integrity. • Access Management: Strict access control policies and multi-factor authentication should be applied to systems operating within the infrastructure, ensuring that only authorized personnel can access critical ICT systems. 4. Asset Management and Inventory Control • Asset Inventory: Maintain an updated inventory of ICT assets, including hardware and software, with records of their configuration, purpose, and associated risks. • Patch and Vulnerability Management: Organizations must ensure regular updates and patching of ICT systems to mitigate vulnerabilities that could be exploited by cybercriminals. 5. Incident Response and Reporting • Incident Response Plan: A detailed incident response plan must be in place for detecting, responding to, and recovering from cybersecurity incidents involving ICT infrastructure. This includes protocols for incident classification, escalation, and resolution. • Incident Reporting: Organizations must have a procedure to report cybersecurity incidents, in compliance with the Cyber Security Act, the relevant EU regulations, and the CSIRT (Computer Security Incident Response Team). This includes timely reporting to national authorities when significant incidents occur. 6. Personnel Security and Awareness • Employee Training: Employees must receive regular training on cybersecurity practices, including awareness of phishing, password policies, and physical security of ICT systems. • Role-Based Access Control: Ensure that only personnel with the necessary permissions are granted access to specific ICT systems, based on their job roles and responsibilities. 7. Supply Chain Security • Third-Party Risk Management: Measures must be in place to evaluate and manage the cybersecurity risks of third-party vendors or service providers that may have access to ICT infrastructure. This includes performing due diligence on vendors' cybersecurity practices and establishing contractual agreements regarding security responsibilities. 8. Compliance with EU Cybersecurity Requirements • Alignment with the EU NIS Directive: Ensure compliance with Directive (EU) 2022/2555, which mandates that essential services and digital service providers (such as operators of critical infrastructure) implement measures to protect the security of network and information systems. • Cybersecurity Certification (Regulation (EU) 2019/881): Organizations should comply with the requirements of Regulation (EU) 2019/881, which provides a framework for ICT cybersecurity certification. This may involve obtaining certifications for critical ICT assets, demonstrating that they meet certain cybersecurity standards. 9. Documentation and Reporting • Cybersecurity Policies and Procedures: Comprehensive documentation of all cybersecurity measures and procedures must be maintained, including risk management processes, security policies, incident response protocols, and audit records. • Audit and Compliance Checks: Regular cybersecurity audits and compliance checks must be performed to ensure that the infrastructure remains secure and aligned with both national and EU cybersecurity regulations. 10. Monitoring and Logging • Continuous Monitoring: Continuous monitoring of systems and networks for anomalies or breaches is critical. Tools for Security Information and Event Management (SIEM) should be employed to monitor and log activities across the ICT infrastructure. • Audit Logs: Comprehensive logging of system and network activities must be maintained, including user activities, system events, and incidents. Logs must be stored securely and made available for audits. | Yes, it is possible, and we have already implemented in some projects before. | Yes, it is possible to configure the integration of the system with an external central system for collecting logs provided by the Client, such as Splunk. For this implementation, it is required collaboration with the client, who manages this external system, to perform this configuration and correctly evaluate the implementation tasks. Once clarified the purpose and type of information to be collected the central log solution could be detailed. | The main design criteria of the TMS control level solution are based on the deployment of a state-of-the-art virtualization-based platform, providing high performance, environment isolation, scalability and flexibility and redundancy and high availability. The IT solution has been designed to provide Redundancy and High Availability at different levels, providing failover protection in case of failure of any critical element of the architecture (hardware or software failures): • Locally in each datacentre (Prague and Přerov) we will consider: o Hardware redundancy: All critical elements of the IT Platform are redundant to avoid Single Points of Failure and to ensure that operation is not affected in the case of failure of single components:  The platform is made up of several physical nodes  Disks are configured in redundant way  Network/Storage paths and power supply are redundant. o Virtualization solution: Ensures the high Availability for virtual environment defined for TMS Control level solution. The platform will be sized and configured to ensure the service in case of failures in virtual or physical servers minimizing the impact on the service. o Application and database services of the Operation/Production environment will be configured to provide high availability at service level. • Additionally, to the local availability defined on each datacentre, the solution provides Geographical redundancy: o Geographic Redundancy and High Availability: we will consider an Active-Standby configuration between both datacenters (Prague and Přerov) considering one Main datacenter and the other one as secondary or Disaster Recovery datacenter. Main Operation/Production functionalities are replicated in the Secondary center providing a secondary platform to become live in case of major failures in the main datacenter. o A manual procedure will run the services in the secondary datacentre The proposal includes a Backup Solution for data protection, this system will allow the recovery of the system to a previous state, if required: • A State-of-the-art disk-based backup solution with dedicated hardware for data protection. • The solution will protect VMs (snapshots), filesystems, Kubernetes services and database information It is assumed that communications between the data centres where the TMS Server solution will be deployed (located in Prague and Přerov) are out the scope of the proposal, being the responsibility of Správa železnic. We need confirmation about this connection (latency, bandwidth, network extension possibilities) We need to confirm if it is feasible to have a third site to study different possibilities of geographic high availability of the TMS solution. Due to the distance between both centres, Prague and Přerov, which directly affects the communication between them, and therefore the geographic high availability solution, is it valid to propose an active-standby solution between centres with manual failover, providing a RPO that tends to 0 and reducing switching times? We need to confirm whether it is required that the IT platform be an exact replica in both sites (Prague and Přerov) or if, on the contrary, it is valid to configure one of the datacentres as Disaster Recovery, allowing to optimize hardware and software resources in this secondary centre, assuming that it would only come into operation temporarily in case of a major failure in the main datacentre. The TMS is designed to be a highly available system, as it contains mission-critical functions. This availability requires the system to operate 24x7, with downtime limited to planned maintenance periods. The specific target for HSL operation availability is 99.99%. | At service level, the Redundancy and high availability provided by the ICT platform to be deployed in the Prague and Přerov Datacentres, have been described in the answer to question 2.1. The workstations for operation and TMS management will have connectivity to both datacentres, so they will be able to connect to the service regardless of which datacentre is active at that time. In case of workstation failure, the system has the capacity of distributing dynamically the areas of control, using the sectorisation function. That way any other workstation can take over of the control area belonging to the failing workstation and let the system to continue the operation without any interruption. | As detailed in the answer to question 2.1, at the ICT level, the solution has been designed to offer redundancy and high availability at different levels: • Locally in each datacentre (Prague and Přerov) we will consider: o Hardware redundancy: All critical elements of the IT Platform are redundant to avoid Single Points Of Failure and to ensure that operation is not affected in the case of failure of single components. o Virtualization solution: Ensuring the high Availability for virtual environment defined for TMS Control level solution. o Application and database services of the Operation/Production environment will be configured to provide high availability at service level. Additionally, the microservices based architecture of the system allows to ensure that critical services are always working, and scaled to the workload at all times • Geographic Redundancy and High Availability: we will consider an Active-Standby configuration between both datacentres (Prague and Přerov). Data will be replicated in both datacentres. A manual procedure will run the services in the secondary datacentre. | Yes, this is a common task in our projects. | To answer we would need more information: - Workload analysis: expected task load and time. - Level of automation expected. - Dynamic control areas operation. With the information provided and taking into account our TMS level of automation and functions we think maybe it is required a smaller number of workstations. We miss some workstations/workplaces for maintenance and Training tasks | For some projects line and traffic controller corresponds to the same operator and therefore the same workstation. Our TMS allows both approaches (line and traffic separated or line and traffic merged into a traffic manager). | Our TMS allows total free distribution among workstations and CPDs so it is possible to design the initial distribution regarding operational and organisational principles. Taking into account this, having most of the operation in on CPD ease human resource management and energy considerations. | We miss some staff: • Passenger Information Manager to monitor and control all the information to external channels (station pannels, onboard pannels, public announcement, internet media channels, etc.) • IM-RU coordinator to manage interaction with RU representative. • Supervisor, as the hall chief to coordinate and supervise the operation. • Trainer and maintenance sfaff. | We miss some information regarding the expected operation: • CONOPS • Passenger vs freight • Conflict detection and resolution • TSR/Possession/Isolation • Timetable generation • Relationship between Railway Undertaking and Infrastructure Manager Regarding the redundancy defined for the TMS Control Level solution, we need some information or clarifications: • It is assumed that communications between the data centres where the TMS Server solution will be deployed (located in Prague and Přerov) are out the scope of the proposal, being the responsibility of the Client. We need confirmation about this connection (latency, bandwidth, network extension possibilities) • We need to confirm if it is feasible to have a third site to study different possibilities of geographic high availability of the TMS solution. • Due to the distance between both centres, Prague and Přerov, which directly affects the communication between them, and therefore the geographic high availability solution, is it valid to propose an active-standby solution between centres with manual failover, providing a RPO that tends to 0 and reducing switching times? • We need to confirm if it is required that the IT platform would be an exact replica (identical hardware and software configuration) in both sites, Prague and Přerov, or if, on the contrary, it is valid to configure one of the datacentres as Disaster Recovery, allowing to optimize hardware and software resources in this secondary centre, assuming that it would only come into operation temporarily in case of a major failure in the main datacentre. It is assumed that the IT platform will be designed to provide redundancy and high availability locally in each of the data centres at different levels and that a backup solution will also be considered to recover the system to a state prior to a failure if required. • We need to confirm if an Active- standby configuration between datacentres with a manual failover procedure is valid for the proposal. • We need information about expected RPO and RTO for the failover scenario between datacentres to evaluate the most appropriate solution for geographical high availability. Regarding to the Training environment we miss some information: • We need to clarify if the training environment to be deployed in Prague requires dedicated IT infrastructure separate from the operating environment that will provide service. • We need to clarify how many workstations are required for this non-production environment. • We need more information about the location for this non-production environment, regarding to IT platform to be deployed in a datacentre (servers/storage) and workstations to be deployed in different rooms.
2 | XXX | We have estimated a cost within a range a 12-15 million €. The cost depends on the sizing of the section to be included (number of interlockings, routes, elements of each interlocking etc.), architecture to deploy (redundant nodes with active-active), scope and requirements of the solution etc. NOTE: Although our Company has a proprietary SCADA system, this system has not been considered in the estimated costs. | We suggest extending the timeline for Milestone 1. We believe it could be 24 months from the approval of the requirements and scope by both parties. Based on our experience, the requirements gathering and specification phase requires a series of meetings to clarify and agree on the scope with the clients. This phase often takes a considerable amount of time (we estimate around 12–24 months), which would take place after the contract is signed. After this phase, and once the scope has been approved, we would be able to implement the system within 24 months. | Answer: See attached diagram in Annex 1 | We do not see the communication between the different subsystems very clearly. We understand that there will be an energy SCADA system that will communicate with the field equipment via the communications network to obtain energy status information from the infrastructure. This SCADA will be managed from the PED workstation. The TMS server is the core of the traffic management system. It communicates with the IXL (for field signalling control) and the RBC (for ETCS command management) via the communications network. This server will be integrated with adjacent TMS systems (to send/receive train information) and with external systems that need to send/receive traffic operation data. There will be an interface with the ATO trackside system to exchange train information (route, timetable, etc.) to enable automatic operation. The TMS HMI will be located at the PTD workstation. The ATO trackside system will communicate with the ATO on-board system via FRMCS. An updated diagram can be found below. | Our company can provide the TMS, ATO Trackside, and Energy SCADA systems. These systems are deployed on commercial hardware provided by our company (servers, workstations, storage cabinets). In addition, our company supplies the necessary equipment to set up the operator workstations (PED, PTD, PDŽDC). | Regarding integration with interlockings and RBCs from different suppliers, we propose the use of the standard RaSTA protocol as the security layer and EULYNX SCI-CC as application layer (or an application layer to be jointly defined with the client). For communication with adjacent TMS systems, we have experience in several projects for XXX, integrating with systems from multiple suppliers. This communication is carried out via XXX’s standard MIE protocol. The MIEs operates using a publish/subscribe mechanism, whereby each external client subscribes to the relevant CTC information—for example, to obtain train numbering information and the status of elements at boundary stations. | As stated in the previous response, we propose the implementation of the standard RaSTA protocol, as the SCI-CC interface uses this protocol as a security layer for secure communication. In addition, we would implement the SCI-CC interface and, in case SCI-CC is not sufficiently defined for the needs of the project, we could jointly define a custom application layer with the client. | We understand that this question refers to the communication protocol between the TMS Control Level and the TMS System Core. As mentioned in previous responses, we propose the implementation of the standard RaSTA protocol, along with the possibility of working with the client to define the application layer for communication between the TMS and the RBC/IXL. We have experience in several projects for xxx, in which we have collaborated on the definition of a standard SCI-CC-A protocol for communication between the TMS and interlockings from different suppliers. Additionally, we also have experience integrating our system with proprietary protocols from several suppliers, provided these are open protocols. | Our proposal is to implement standard protocols to enable communication between the TMS and interlockings from different suppliers. | Yes. Our company solution is currently integrated with signalling systems from the following suppliers: <unnamed companies> | We estimate approximately 24 months from the approval of requirements and scope by the client. | We have a base product that includes the essential functionalities typically required in our projects. To this product, we will add specific modules and features to meet the particular regulatory needs of this project. This will result in a generic product for the client, suitable for deployment across all lines and regions within the infrastructure. For each of these lines or regions where the system is installed, only the specific configuration would need to be adjusted. | The requirements outlined in the documentation are very generic. It will be necessary to define the specific functionalities required for the project that are not included within the generic product. There would be no difficulty as long as the scope and requirements are clearly defined. It is crucial that there is a collaborative work with the client. | The entire application is developed in-house. | We do not have experience in implementing this type of system, but we can integrate our TMS with an SCWS system, provided that the communication protocol between both systems is well-defined and open. In addition, our "XXX" has commands that are sent to the interlocking to block sections and track elements when there are track works and maintenance tasks in the track. | We consider 7 years a reasonable time for assessing experience. See Annex 2 for a sample list of similar projects our company has delivered into service in that interval. | We do not supply SCWS systems. However, we could integrate our TMS with a SCWS system, provided that the interface and protocol are well defined and open. | It depends on the sizing of the section to be included (number of interlockings, routes, elements of each interlocking, adjacent TMS systems, etc.). Yes, there is an impact. That is why it is important to work collaboratively to create an inventory of the information we need and determine the format that is most convenient for both parties. | Answer: Yes. We have experience in several projects for XXX, integrating with systems from multiple suppliers. This communication is carried out via an ESB bus using XXX standard MIE protocol | We are open to provide long term (20+ years) technical service and maintenance support, like we are doing in other projects. We believe it is the best way to assure the Client the continuous evolution of the solutions developed for our clients. Selling source codes is not part of our company common practices, due to the sensibility of IPR, but we could negotiate these matters as part of the Contract. Co-development could also be contemplated. | Up to a certain point of complexity, training and practice can be transferred to the Client, so it can perform simple and common maintenance proceedings. But even if we did provide the Client with the source code and ownership rights, future developments imply a high level of responsibility and require years of expertise. Only highly trained and experienced designers and programmers, following stringent development procedures, can meet the quality and safety requirements TMS systems require. As said before, it would take years of experience and a broad team of experts to achieve the technical support that our company can provide. | open to be discussed during contract negotiation. We recommend long term support, i.e. 10 years technical support and maintenance on similar projects. | Factors such as the technological obsolescence of IT equipment and new functionalities/requirements from the client. We have experience with projects for XXX and other clients, both in upgrading obsolete systems and in projects tendered with 20-year maintenance contracts. We create obsolescence plans at the product level to plan the service life of the equipment. At the project level, we work with clients on technology management to ensure system maintenance throughout their lifecycle. | in addition to the training and handover procedure to be defined in the Contract, we could assure the availability of the source codes for special contingencies using an escrow account or similar option. | Our company has developed the XXX platform as an integration solution for multifunctional control centres. This platform includes a messaging system based on an ESB integration bus that uses the JMS standard (XXX ESB), enabling communication between different heterogeneous systems and facilitating the exchange of information and functionality between them through XML messaging. | Our TMS solution complies with the requirements of: Regulation (EU) 2024/2847 of the European Parliament and of the Council of 23 October 2024 on horizontal cybersecurity requirements for products with digital elements and amending Regulations (EU) No 168/2013 and (EU) 2019/1020 and Directive (EU) 2020/1828 (Cyber Resilience Act). Directive (EU) 2022/2555 of the European Parliament and of the Council of 14 December 2022 on measures for a high common level of cybersecurity across the Union, amending Regulation (EU) No 910/2014 and Directive (EU) 2018/1972, and repealing Directive (EU) 2016/1148 (NIS 2 Directive). “IEC 62443 3-3” SL-2. | Yes, it’s feasible. | Yes, it’s feasible. Preferably using RFC 5425 (Syslog TLS) or RFC 5426 (Syslog UDP). | Our company TMS can be deployed in redundant physical configurations in both ‘active-active’ and ‘hot-standby’ cluster modes, ensuring a high level of availability. This architecture includes a single CTC composed of two redundant nodes located in separate locations. Each node is equipped with redundant hardware and is capable of managing railway traffic across the entire project scope. This architecture enhances system availability on two levels: • Each node serves as a backup for the other. • Each node is fully redundant, featuring high-availability hardware with communication and power redundancy. Availability largely depends on the architecture each client requires. In projects with demanding architectures, such as those for XXX, where a redundant two-node architecture has been implemented, a RAMS analysis has been carried out to determine the availability value, the resulting availability is 99.99999% (percentage of time the system operates relative to total time). | Our TMS provides an "active-active" solution consisting of two CTC nodes located in different locations (for example, Prague and Přerov), connected to each other. Each node, in addition to controlling its own area, will act as a backup for the other. In the event of a node failure, the other node would be able to take control of the interlockings of the failed node. The operator workstations are also redundant (there would be backup workstations from Prague in Přerov and backup workstations from Přerov in Prague). Additionally, there is control zone management. Each operator workstation is assigned a specific area of responsibility and controls the interlockings in that zone (the workstations in Prague will control the area assigned to that control centre, and the ones in Přerov will control their corresponding areas). In the event of a workstation failure, the responsibility for that area will be transferred to another workstation, generally the supervisor of the control centre, who can assign the zone to another operator workstation (for example, if an operator workstation in Prague becomes unavailable, another workstation in Prague could take control of the affected area). In the event of a total node failure, the backup workstations of the other node would take control of the responsibility areas of the unavailable workstations. | We use virtualisation tools such as XXX or XXX and the HA Add-on, which provide High Availability functionalities. At the hardware level, we design a redundant node architecture (composed of two identical semi-nodes, which can be optimised by calculating an N+1 server sizing). | TMS Application: Our solution is flexible to adapt to the needs, although we require more details about the specific functionality to be implemented, as the requirements specified in the documentation are very generic. Architecture: We would implement the architecture we proposed in question 4. Operator workstations: we fulfil the requirements without any issues. | Based on the information provided (noting that we do not have the layout maps) and considering our experience, the proposed solution appears to be feasible, and the kilometres-per-workstation ratio seems reasonable. However, this will ultimately depend on the size and complexity of the interlockings to be controlled. | In principle, yes. It depends on the size of each individual line. Nevertheless, our TMS implements a control zone management functionality, which allows for the redistribution of areas of responsibility among the various operator workstations in case of fluctuations in traffic density across the lines. | In principle, yes. It depends on the size of each individual line. Nevertheless, as indicated before, our TMS implements a control zone management functionality, and is deployed in an “active-active” architecture (see question 2 from “System availability” section) that help to make system operation more flexible. Moreover, thanks to the standardisation of the multi-user workstations, the Single Sign-On (SSO) solution, and the CTC HMI, the versatility of the system is enhanced, as any user can log in with any profile from any workstation. This minimises system unavailability in the event of a hardware failure in any of the workstation components. | In principle, yes. It depends on the size and traffic of each individual line. Nevertheless, as indicated in the previous question, our TMS implements different features that help to make system operation more flexible. | The specified requirements are very general. We have a rough idea of what is needed, but it would be necessary to have a detailed list of the specific functionalities required (e.g. whether traffic regulation is needed, conflict management, which ERTMS commands must be implemented, etc.), so that all suppliers can provide comparable offers. Based on our experience, the specified operation can vary significantly from one client to another.
3 | XXX | Parameters that could drive the budget: • Complexity and specificity of functions (our offer includes very adaptable solution, that generally speaking could satisfy customer’s needs). • Complexity of topology. • Key indicators (see section 3, question nr 5). • Availability and format of data (schematic plans, list of controls/indications etc). • Integration complexity (if there are specific external systems). | Yes, we consider this schedule achievable, and then we propose to start the deployment with pilot section to facilitate training of operators, to support them in the transformation of operational rules and acceptance by the operators. Depending on the complexity of integration with external systems, the relevant activities should be included in the schedule. | Schedule in Appendix 4 is good enough, pending all agreed inputs (topology data, schematic plans, list of indications/controls for each station, route tables) are made available. | Network connections should be more detailed, at least to understand level of redundancy; infrastructure characteristics shall be detailed. | ATO, JDKnet, JDK Proxy and DOSTI server are generally not part of the TMS solution; this is based on our experience, it has to be reviewed in a specific context. | As already identified by SŽ, EULYNX is the main driving force behind the standardization of interfaces between different systems in the European Union. The EULYNX specification in general, and EULYNX SCI-CC specifically for communication between "TMS Control Level" and "TMS System Core," is the recommended protocol. | Maybe no adaptation is necessary, it depends on external systems maturity referred to EULYNX: for example, the process data interface level is supplier independent, therefore it shouldn’t need specific adaptation. | We are, we have references for HS lines in Europe as well as in Asia. | We have components that are flexible enough to fit with different market's needs. | <unnamed companies> | The development timeframe strictly depends on the features and requirements included in the final specification: the estimated maximum timeframe is 3 years. | According to our understanding, the requirements are manageable through existing configurability features of our portfolio, well adapted to all classes of market needs. | We require the system to be adaptable to new technological solutions that may emerge in the future” --> We are strong innovative TMS company, therefore we are close monitoring of technological trends and we have a roadmap for evolution of our solutions. “Immediate redundancy – in the event of a failure of one site, the other site must automatically and take over control without delay.” --> Based on our experience, this type of redundancy mechanism is needed in business continuity scenarios, where we propose a 3 sites architecture. The TMS must respect the principles of cyber security defined by applicable EU and Czech legislation and internal regulations of Správa železnic. --> see answer on cyber questions (26, 27 and 28). “…in the event of a cyberattack on any of these CDP TMS for HSL, the TMS must also react in a safe manner and immediately close the CDP that has been attacked from operation control.” --> It’s safe, as per safety requirements allocated to TMS. | Delivered by single contractor. | We understand this is a system to warn personnel on the track (maintenance people) that a train is approaching. Yes. The most advanced TWS level SCWS – is implemented on another continent with: •Possession Management •Temporary Speed Restriction Management •Track Marking Management •Rail Objects Management •On/Off-Tracking Management •Trains Management •Location Tracing •Geofencing •Position Validation For an unnamed country, there is Mobile solution for locking/unlocking the Working Area (Interlocking logic) for preventing train movement within that zones – plus geolocation of the operator These solutions can be easily adapted to the existing infrastructure and integrated with systems such as Interlocking or RBC. | Sample of Projects within the last 7 years: several projects. | Same as question 15. | Isn't this an extension of line? If that's the case, we'd say that using the same data format from the previous sections already deployed facilitates the addition of a new section. | Yes, the Bridge component is flexible enough: if protocol is defined, it’s possible. | Our company is committed to sustain its customers over long term and is particularly offering long term service agreements including on the Software. However, we do not transmit any access to the source code to avoid notably any loss of integrity if modifications are done without our supervision. | As per above answer, we offer Software life cycle management services that allow our customers to implement modifications according to their needs, manage obsolescence, implement security patches, etc… | The duration of the support period is defined case by case with our customers. We can typically offer long term support for 15 years or more for such systems that allow to cover obsolescence of Hardware (eg servers, monitors, etc…) or Software (eg Operating Systems) while bringing corrections, patches (eg security) or evolutions driven by new operational needs. | Answer: The lifetime of the system is driven by: - The Hardware obsolescence of COTS - The Software/OS componentes obsolescence - The Cybersecurity constraints (vulnerability management and maintain effective defence concept) - The lifecycle management strategy (updates, upgrades, End of life stocks, techno refresh, ,…) The lifetime before techno refresh for this kid of systems is typically around 7 years. We generally define the strategy in agreement with the customers. Experience: we have few long-term support contracts including similar systems. Our recommendation is to define properly the scope of the contract to avoid impairing the customer or the supplier. | Our company is generally not facing this type of exit but is committed to maintain long time relationship with its customers. | Our solution has a highly configurable component (Bridge) which manages the communication with external world, the role of the component is to: • subscribe to data notification • convert and merge information based on the specific request of each external system attached to the Enterprise Service Bus (ESB) • shadow the TMS internal business logic from the external system • receives data change request from the ESB and applies them to the TMS • manages multiple connection protocols in order to be able to adapt to every possible customer’s need The communicator architecture is mainly based on XML formatted data, which publish the whole information. XSD are defined for each published XML, allowing the validation of information. | Yes, we are able to meet these requirements. | Yes, usage of a centralized Active Directory for authentication and usage of SSL certificates are fully supported by our company products depending on criticality of the connection. We suggest not fix the selection of specific encryption algorithms (like ECDSA) considering the continuous evolutions/improvements in such area. | Yes, it is feasible. Details of implementation depend on the Central System. | We can ensure high availability by using two nodes in hot standby availability model. Typical availability for platform superior or equal to 99,998% reached. | This should be allowed by georedundancy configuration. When workplace relates to a workstation, then an operator from another workstation can take over the workload of the failed workstation by simple operational procedures. If “workplace” is a node of the OCC, the hot standby redundancy makes the consequences of this failure transparent to the operator. | We use a hot standby availability model inside the OCC, where the loss of one node is transparent to the operator. | : As of the available documents and the experience presented hereby, we can say that it is highly likely that we are able to fulfil the requirements of yours. To add to that, it is understood that the process of supplier selection will allow for more detailed understanding of Customer’s needs and capabilities of the supplier in order to find the most suitable solution. | It seems balanced and consistent with our experience on similar projects. Confirmation of these figures (13 workplaces in one OCC and 15 in the other) will be subject of design phase. | We usually confirm the design of workplaces against efficiency and ergonomy in the design phase. | We usually confirm the design of workplaces against efficiency and ergonomy in the design phase. | We usually confirm the design of workplaces against efficiency and ergonomy in the design phase. | Any availability of preliminary conceptual operation would be appreciated to allow pre-sizing of the solution.
4 | XXX | Providing a precise cost estimate for implementing a TMS without a detailed understanding of the required integrations and system specifications is challenging. However, based on our experience with similar large-scale railway infrastructure projects, we can offer a preliminary cost range and outline key factors that influence the total investment. Preliminary Cost Estimate Based on the information available at this stage, we estimate the total cost for implementing the TMS—including hardware, software, integration with existing systems, staff training, and associated project activities—to fall within the range of €20 to €35 million. This range is indicative and may vary depending on several factors, as outlined below. Key Cost Drivers A. System Integrations and Interfacing Requirements The number and complexity of required interfaces with existing signalling systems, IT platforms, and legacy infrastructure can impact cost. Well-documented and standardized interfaces reduce integration time and cost. B. Quality and Availability of Input Data Comprehensive and timely delivery of up-to-date technical documentation, including signalling protocols and interface specifications, is essential for efficient system integration. Insufficient input data can lead to increased development time and costs. C. Resource Allocation and Collaboration A key success factor in past projects has been strong resource commitment from both Cactus Rail and the customer. Ensuring adequate staffing on both sides—especially for domain experts, project managers, and technical staff—is vital to maintain timelines and manage risks. D. Localisation and approval processes A thought-out approval process by the relevant authorities is essential for the successful deployment of any railway system. This process is typically managed by the infrastructure owner, who is responsible for coordinating the necessary approvals. The supplier plays a supportive role by providing detailed input and clarification on system-specific aspects, ensuring that all technical and safety requirements are thoroughly addressed. | In general, we find the proposed schedule in Appendix 4 to be ambitious and well-structured. The timeline reflects a logical sequence for the TMS project’s implementation, particularly considering that most of the supplier's efforts will be frontloaded, occurring prior to the deployment of the first system. This effort likely spans milestones 2 and 3, where foundational system components and integrations are developed. However, we would like to highlight a few critical considerations that should be factored into any final scheduling decisions: A. Integration Complexity: The project involves interfacing the TMS with both new and legacy signalling systems, which inherently introduces technical and documentation-related uncertainties. Experience shows that such integrations often take longer than anticipated, both in development and in formalizing the required documentation and approvals. B. Risk of Overly Tight Scheduling: We strongly recommend avoiding an overly aggressive timeline, particularly for milestones that is in need of input data of good quality. A compressed schedule in these areas could lead to implementation challenges or delays later in the project | To ensure a robust and structured system delivery process, we recommend expanding the milestone framework between stages 1–4. Key additional milestones should include system design, testing, verification, and approval. These steps are critical to ensuring that the system meets functional and technical requirements, and that potential issues are identified and resolved early. | See further detailed in 2.1. | To provide long term control, we recommend introducing integration layers between the different systems such as interlockings, passenger information and planning systems. This would enable all subsystems to be managed as independently, improving maintainability and making it easier to modify or replace individual subsystems in the future. | To enable seamless integration between the TMS and future signalling systems from various manufacturers, we propose using "XXX" —a proven industrial integration platform developed specifically for the railway sector. "XXX" – Vendor-Agnostic Integration "XXX" is already in implementation by an unnnamed company, serving as a generic communication layer that standardizes data exchange regardless of the underlying signalling system’s brand, age, or protocol. This means the TMS receives consistent, unified data from all connected systems, simplifying integration and reducing lifecycle costs. Built to scale from local installations to national systems across multiple data centers, CCS supports both brownfield and greenfield projects—making it ideal for modern railway infrastructure such as the new high-speed lines in Czechia. Standards and Protocols We suggest using: • EULYNX and ETCS/RBC protocols for compatibility with modern signalling technologies. • Modern IT communication standards like REST APIs, MQTT, and standardized data formats (e.g., JSON, XML). • CCS's generic interface layer to future-proof integrations and isolate the TMS from vendor-specific complexities. The combination of TMS and "XXX" offers a future-ready, cost-effective solution for integrating diverse signalling systems—well suited for both existing networks and new high-speed rail projects in Czechia and beyond. | We will use the "XXX" platform which is described in several places in this document. This platform is described in more detail in questions 6 and 10.. | Our company has an extensive track record in both the development and implementation of communication protocols within railway environments. This includes interoperability frameworks, real-time signaling interfaces, and protocol mediation between control and execution layers. These capabilities ensure that we are technically and operationally well-equipped to support this initiative in collaboration with Správa železnic. | Our integration platform “XXX” is an integrated part of our TMS. “XXX” enables seamless integration across rail systems of any brand, age, or protocol — all through a unified communication layer. At the core is a global object model that provides a consistent, system-wide naming convention, independent of the equipment’s type or manufacturer. This abstraction not only simplifies operations today, but also ensures a smooth transition to future upgrades. As infrastructure is modernised, the object model is already prepared to accommodate new capabilities — without the need for reengineering. “XXX” employs a robust microservices architecture, utilizing container technology and a high-performance event streaming platform to ensure highly reliable, real-time communication. This modularity supports scalability and allows independent updates, adapting smoothly to operational needs. The platform can interface effectively with all types of signaling equipment and interlockings, irrespective of their brand, technology, or age — ranging from relay-based to modern computerbased systems. In the next answer we list different signalling systems that are integrated into the platform today. | Yes, we guarantee compatibility with signalling systems from at least three different suppliers without requiring EULYNX-type solutions, thanks to our use of "XXX" —a powerful, vendor-agnostic integration platform purpose-built for railway operations. Proven Multi-Vendor Integration "XXX" is designed to act as a generic communication layer that abstracts away manufacturer-specific protocols, enabling seamless integration with a wide range of signalling systems. This allows our TMS to interface with a diverse set of systems while maintaining consistent data flow and operational logic at the upper level. Supported Signalling Systems Today, our system has demonstrated compatibility and successful communication with signalling solutions from multiple leading manufacturers, including: <unnamed companies> Our TMS, when paired with the "XXX" platform, provides robust, field-proven compatibility with a broad range of signalling systems from different suppliers—without relying on EULYNX-type standardization. This ensures a flexible, scalable solution that is well-suited for both legacy infrastructure and future expansion projects. | Our company has implemented new traffic management systems within timeframes ranging from 18 to 48 months, depending on system size and the complexity of external integrations. | In these cases we recommend using industrial open source. Our company has an in-house process for evaluation these products with regards to maturity and maintainability. | See section 2.1 for more details. | “XXX” anf “YYY” are fully developed in-house by “ZZZ”,which retains all associated intellectual property rights. The system operates on a “XXX” and is virtualized using “YYY” – these are the two primary external components integrated into our solution. However, both components can be replaced if required, offering flexibility in deployment. During the project, we will work with several local suppliers to make use of their knowledge of local conditions and to support implementation, on-site assistance, documentation, and commissioning. This arrangement helps ensure that the project is carried out in a way that aligns with local requirements and conditions. | No, it has not been a requirement in our existing projects. | During the last seven years our company has been working on several projects similar to the scope of this. Below is three projects listed. (left anonymous). | TBD | Estimating the financial and time requirements for connecting another HSL section to an already functioning TMS largely depends on the specific scope of the project. However, it is generally significantly less costly and time-consuming than implementing the base system, as this phase would primarily involve configuration rather than new development. This distinction greatly reduces both complexity and effort. The format of the data provided does have an impact on the implementation process. Using the same data format as the first section is preferred, as it helps maintain a homogeneous and consistent integration process. Uniformity in data structure can reduce errors, simplify configuration, and accelerate deployment. If a different data format is provided, it is still manageable, but it would require the use of our existing integration platform. This platform has been previously described and is designed to bridge differences in data formats, though it may involve additional effort compared to working with a consistent format. | Yes, integration between our TMS and a third-party TMS is technically feasible and supported. While this functionality is not currently utilized by any of our existing customers, it will be implemented in an upcoming unnamed project. This integration will be carried out using our integration platform, "XXX", which has been described previously | We recognise that long-term control and operational independence are key considerations for critical national infrastructure. As an independent and specialised supplier, we see this as an opportunity to offer differentiated value beyond traditional licensing models. In addition to long-term support, maintenance, and lifecycle services, we are open to negotiating the sale of source code for use within your own installations. This would give you the ability to: • Secure long-term control over system management and evolution. • Reduce dependency on us as the sole supplier. • Enable future adaptations in line with your operational needs. Such a model would give you the right to use, maintain, and develop the system internally or through third parties, exclusively for your own operations, while we remain available to provide ongoing support and expertise under agreed terms. We are open to discussing this further for both the TMS and the "XXX", either separately or as a combined package, depending on your preferences. We believe this approach can create long-term value and security for your organization while enabling a strong and supportive partnership with us going forward. | We understand the need for long-term operational security. However, we are not in a position to transfer ownership of the intellectual property, as ownership must remain with a single legal entity and cannot be split across multiple parties. This ensures that the IP retains its legal and commercial integrity, which is critical for us and all customers who rely on the system. To meet your needs for operational independence, we offer secured access to the source code via a source code escrow agreement. This ensures that, in the event we are no longer able to support the system—such as in a bankruptcy situation—you would receive full access to the source code and documentation. This would allow you to continue using, maintaining, and developing the system within your own organisation or with a partner of your choice. We believe this model provides you with practical long-term control without requiring a formal transfer of ownership, which would not be feasible for us or our other customers. | A 25 years’ service and support agreement is common for this type of project. | Proper maintenance is essential for extending service life. We recommend signing a separate maintenance agreement that covers new versions and adaptations to new HW versions. The company has extensive experience in providing maintenance support. | We foresee that an exit or transition can be supported by a structured Winding-up Plan developed together with the customer, aimed at ensuring continuity of operations with minimal disruption. This plan would typically include knowledge transfer, handover of system documentation, and support for new procurement or onboarding of a new supplier. We are prepared to provide commercially reasonable assistance, including access to documentation, data, and key personnel, to secure a safe and orderly transition. Specific responsibilities, timelines, and acceptance criteria would be defined jointly in the winding-up phase to meet customer-specific requirements. | We would use our integration platform "XXX" for integration in this project. This platform is described further in questions 6 and 10. | We acknowledge the cyber security requirements outlined in your RFI and understand their importance for the safe and secure operation of the TMS. Our development and delivery processes are based on recognised railway standards such as CENELEC EN 50126 and TS 50701, which include both safety and cyber security considerations. We also follow customer-specific safety and security management procedures as part of project execution. At this early stage, we have not yet fully assessed all implications of the referenced national and EU cyber security legislation. However, we are committed to working with you in the next phases to ensure alignment with these legal requirements, including Act No. 181/2014 Coll., Decree No. 82/2018 Coll., Directive (EU) 2022/2555, and Regulation (EU) 2019/881. We look forward to receiving further clarification of your specific expectations and procedures in the coming stages. | We confirm that integration with customer-provided Active Directory (AD) services for access control is generally feasible and in line with common practice in similar deployments. This enables centralised user management and authentication, which we consider beneficial for operational security and administrative efficiency. Regarding secure communication, we anticipate that the proposed system will be able to support SSL/TLS using certificates issued by an internal certification authority (CA). The use of the ECDSA algorithm is increasingly supported in modern platforms and is aligned with current security best practices. However, specific feasibility may depend on the detailed system architecture, selected components, and customer-specific infrastructure requirements, which we expect to clarify in the next project stages. At this stage, we do not see any fundamental barriers to supporting these mechanisms but reserve the right to validate technical details in cooperation with you as part of the design and integration phase. | A connection to a central log collection system like SPLUNK is possible, as long as it is implemented in a secure and appropriate manner. Today, we use data diodes to ensure one-way traffic when connecting to external systems. As long as the SPLUNK connection follows this principle, there are no technical obstacles. | To ensure high availability of the TMS system, we employ a multi-layered, redundant system architecture. This includes the geographical separation of primary and backup control centres, each equipped with both active and reserve traffic management systems. These centres can be flexibly located, provided that high-quality network connectivity to the data centres is maintained. All operator workstations—whether in active use or not—can be used for system monitoring and support functions, ensuring continuous operational awareness. The software is deployed on a virtualisation platform that provides automatic failover between active and standby units, helping to minimise service interruptions. The system operates on an enterprise-grade Linux platform for both servers and clients, ensuring a stable and maintainable environment. The architecture is designed for high availability and fault tolerance, capable of handling both individual component failures and larger disruptions such as the complete loss of a data centre. Integrated monitoring tools continuously track system health and generate alarms in the event of any faults. The modular design enables replacement or updates of components without impacting ongoing traffic management. Final availability targets and commitments will depend on the agreed system architecture, redundancy level, operational setup, and customer-specific requirements, to be defined in the next phases of the project. | See answer in the question 2.3 | Fault tolerance is achieved through the use of a virtualised platform that provides automatic failover between active and standby instances of the system. This allows seamless transition of operations in the event of hardware or software failures, helping to minimise service interruptions. The system is designed with geographically separated data centres or control locations, enabling continuity even in the case of a complete site failure. It further supports redundant system layers that allow individual components to be restarted, replaced, or upgraded without disrupting live traffic management. Monitoring tools continuously track the health of all system components and trigger alarms in case of detected issues, supporting early detection and response to prevent service impact. This architecture ensures the system can tolerate both single-point failures and larger-scale disruptions, securing stable operations over time. | Providing fully equipped traffic control room centres is not part of our standard delivery scope. However, we have experience working with different customer environments and are able to advise on technical integration, layout considerations, and operator workflows to ensure full compatibility with your Traffic Management Concept and functional requirements. We recommend that the physical control room infrastructure (such as building, furniture, and environmental systems) be sourced from local specialist suppliers, while we focus on delivering and integrating the Traffic Management System (TMS) and operator workstations into the agreed environment. | Viz odpověď v 3.1. | See answer in 3.1. | See answer in 3.1. | See answer in 3.1. | See answer in 3.1.
5 | XXX | At this stage of the planning phase, it is difficult to estimate the costs for a complete project. Initial system planning shall identify the requirements for the system, stating clear functional requirements that the system must fulfil. If the requirements follow closely the common standards and existing practises for the TMS systems, the development phase will be shorter. More complexity, new features and integration to other systems will equally increase the development and testing time, increasing the project costs. Typically, in similar projects the biggest challenge is getting the initial data, e.g. engineering design, requirements, track layouts and other data, that is required for the supplier development phase. The more there are third party integrations, the more verified initial data, such as mentioned above, is needed. Hardware prices follow the technical requirements for the system architecture and cyber security. Total TMS delivery scope shall be described very clearly to point out the responsible party for every delivery area. For example, who takes care of the communication network and who secures that the equipment rooms meet the electricity, air conditioning and safety requirements. A clear scope of works table enables the Suppliers to make most cost-efficient offers. | Generally, we agree with proposed milestones and deadlines, for detailed comments and a proposed percentage distribution of the project amount across milestones, please see our attached document MYY-029569 Schedule review. | The indicative schedule that includes the milestones outlined in Appendix 4, as well as additional key milestones we consider essential for the successful completion of the project, are provided in our attached document MYY-029570 Indicative Schedule. Document MYY-029570 Indicative Schedule includes an abbreviation CA which stands for Customer Approval. CA is an approval process which includes key review and acceptance stages to secure project alignment with customer expectations. One approval stage can include not only one, but multiple areas of the ones listed below: - Review of Project Plans: Evaluation and approval of initial project plans to confirm scope, timeline, and objectives. - Requirement Analysis: Review with customer all requirements to create a common understanding for their implementation. Create requirement apportionment to different functional areas. - Preliminary Design Documentation: Assessment of early-stage design documents to validate concepts and feasibility. - Detailed Design Documentation: In-depth review of comprehensive design specifications to ensure technical accuracy and compliance. - Hardware Component Acceptance: Inspection and approval of hardware components to verify quality and specifications. - Testing Phases: o Factory Acceptance Testing (FAT): Verification of system performance at the manufacturing site. o Site Integration Testing (SIT): Validation of system integration and functionality at the installation site. o Site Acceptance Testing (SAT): Final confirmation of system performance and compliance at the operational site. Each CA stage requires customer sign-off to proceed, ensuring alignment with project requirements. | The SZ’s presented architecture is well defined with the sub-systems and networks. Our company is proposing to enhance the representation with a more streamlined geo-redundant architecture aligned with current technological evolutions. Additionally, our company believes it is important to show how the Electrical System controller (PED) will manage the power as these systems are not traditionally controlled directly by “TMS System Core” layer or “TMS Servers” in TMS Control level. These systems need to be part of the complete “TMS Control level“. We feel that it is more important to present the roles (Electric System, Line Control and Diagnostics and Maintenance) and their interactions with different systems as part of their roles. In the Electric System and Diagnostics and Maintenance roles, the responsible need to interact primarily with their respective systems and secondarily need to get information from TMS system. The TMS System with their TMS Servers handle all the communications towards “DOSTI”, “ATO” and “TMS System Core”. | “XXX" TMS product is a modular Rail Traffic Management solution. The system is capable to fulfil all the requirements presented in the Appendix 2 for TMS Control Level in the domain of “Rail Traffic Management and Operations”. The system supports EULYNX communication specifications SCI-CC to communicate with CORE FSS/IL and RBC for ERTMS L2 with future support for Hybrid Train Detection (HTD). The system is also capable of interfacing with Electrical Power systems to monitor the power voltage and able to communicate with the Diagnostics systems to bring all the required data in one place for easy decision making. The system has ATO-TS module which can communicate with the ATO-OB in trains and able to run the trains automatically according to currently defined timetables. | As SZ has already identified, EULYNX is the main driving force to have standard interfaces between different systems in European Union. EULYNX specifications in general and EULYNX SCI-CC specifically for communication between “TMS Control Level” and “TMS System Core” is the recommended protocol. | agrees with SZ proposal to use EULYNX SCI-CC as the main interface to communicate with Central Safety System (CSS/IL/RBC aka. SZ’s “XXX”). Our company has deep understanding of the EULYNX SCI-CC and its advantages and limitations when communication with a Central Safety System (CSS/TMS System Core, ILS/RBC). Depending on the functionality of the procured CSS system for HSL, the standard EULYNX SCI-CC interface may need to be enhanced by customer or RBC/IXL vendor according to the project’s and customer’s specific needs. SZ as participating IM in EULYNX, can propose to enhance the SCI-CC specifications for whole EU or can specify their national enhancements based on HSL environment. In both cases, our company can identify the technical challenges for the interface and what is required to update/add in the SCI-CC specifications to overcome such challenges. The actual process includes looking at the HSL’s requirements for “TMS Control level”, comparing them with “TMS System Core” and evaluating them to ensure each requirement is supported in EULYNX SCI-CC specifications. | Our company will be able to define and develop these protocols based on EULYNX. Our company is currently developing EULYNX solutions for communications between similar layers. Our company´s proposal all the communication between TMS Control Level (layer 1), TMS System Core (layer 2) and TMS Executive level (level 3) should follow the EULYNX standard protocols. EULYNX define specification for communication between all these three layers. Working with vendor and IM specific protocols will be a closed solution with less support for future enhancements. Please refer to EULYNX documentation Document number: Eu.Doc.7_A1 for the whole EULYNX based system architecture. | Our company does not propose an alternate solution for its TMS system to communicate with other signalling systems. In our point of view, EULYNX SCI-CC is the proper protocol to have communication between “TMS Control layer” and “TMS System Core”. Having stated this, our "XXX" architecture and design allow it to support communication with Signalling systems supporting any kind of protocols and able to provide a uniform user experience (HMI) for the Traffic operators. Interfacing with new HSL sections with vendors not supporting standard protocol will require protocol implementation for the specific signalling system. Please see also answer to Question 10 for our "XXX" system capabilities to interface with singling system from various suppliers using supplier’s own protocols. | Our TMS solution is a modular solution and supports communication with Central Safety systems (Signalling and RBC) with EULYNX SCI-CC. In one of the current commercial deployments of "XXX", the system is controlling multiple supplier’s non-EULYNX signalling solutions within a single deployment. Our company does not see any challenges in collaborating and interfacing its TMS system with any Signalling system vendors, as long as the signalling system vendor has fully defined and implemented the safety communication protocols and interfaces for their signalling system. "XXX" supports SIL4 signalling solutions from different vendors including <products of unnamed companies> | "XXX" is a product offered complete set of Railway Traffic Management services and solutions. The system is configured according to customer requirements and infrastructure (physical and signalling). In addition to configuration, customer specific system interfaces (e.g. DOSTI in SZ case) needs to be developed as part of the customer project. Development of the new features and interfaces is possible to do quickly, due to modular architecture. The time for verification and validation of the customer systems (signalling, infrastructure) may depend on the availability of such data. Please refer to answer to questions 2 and 3 for an indicative schedule for the complete delivery project. | "XXX" is a ready-made solution fully capable to be adapted according to our customer’s requirements. As mentioned in answer for question 11, there are aspects of the system which do require application/interface development to adapt the system according to customer’s environment and existing systems. However, these adaptations can be managed in a separate application area which is meant to be customized. | A major part of the requirements mentioned in paragraph 3. “Minimum requirements for TMS” are fully aligned with “XXX” product offering. "XXX" product is a scalable and modular Rail Traffic Management solution based on redundant hardware (HW) clusters located in two different geographical sites. "XXX" supports national as well as ERTMS L1/L2 signalling solutions with automated traffic management based on Automatic Route Setting (ARS) and Automatic Train Operation (ATO). Our company is currently implementing support of Hybrid Train Detection (HTD) for one of our customer. The system is developed and deployed according to cyber security standards to ensure the maximum security for the Traffic Management Operations. Many of the specific requirements for HSL operations are part of the "XXX". | "XXX" is a complete solution with products developed and provided by our company, which has three main parts: 1. Redundant, fault tolerant, commercial Hardware clusters (From Server HW providers) 2. Redundant, fault tolerant, commercial network equipment (excluding the physical fibre cabling between physical sites/control rooms. Our company assume that customer will provide such network infrastructure) product, software modules, operating systems, implementing the required functionality of the system can collaborate with customer in multiple models to share the responsibilities as part of the system delivery. In one model, Our company specify Hardware and Network equipment which can be directly obtained and installed by our customers. Alternatively, we can procure and install Hardware and Network equipment and provide the complete solution. The “XXX” Software solution is based on commercially supported operating systems and is completely offered by our company. | Our company has not implemented the Track Warning System (TWS, but we have studied the topic earlier and concluded the solution can be built with our partner, who has experience in delivering such solution in EU countries. | Our company has successfully delivered dozens of CTC (Centralised Traffic Control) and TMS (Traffic Management System) projects over the course of its 30-year history in railway systems projects. In addition to CTC/TMS, we also deliver level crossing, signalling/interlocking, and object controller systems for the railways, as well as life cycle management, maintenance support and asset management services for these systems. SZ's suggested qualifying period of seven (7) years for reference projects is sufficient for us, especially if the period is counted from the commissioning, final acceptance or start of commercial operation date. If the qualifying period of seven (7) years for reference projects starts from the contract signing date, this could prove challenging for larger projects that often span over several years. In general, we believe a reference qualifying period of 10 years ensures sufficient competition better. We would like to encourage SZ to set realistic and proportionate requirements for the vastness, size, type and the number of required system references, and to consider accepting also on-going projects, especially if several large project references are required. Furthermore, newer systems that are recently standardised by ERA in the latest TSIs and that are not yet widely in commercial operation, such as ATO and HTD (Hybrid Train Detection) should not be included in mandatory reference project requirements or in evaluation, as this would limit the competition. <Three specific projects are listed below – they will remain anonymous> | Yes, it is possible to enhance the TMS capabilities by supplementing it with a SCWS-I. | New sections can be added to already functioning TMS Control Level easily. "XXX" product has been built considering data extensibility and easy scalability for such scenarios. The complete TMS solution is based on "XXX" product and customer specific track infrastructure data and related signalling configurations. The financial impact can be directly related to the time it will take to add new HSL section in the existing system. There can be other factors which can be considered in this scenario such as the new HSL sections’s infrastructure data, TMS cluster hardware and network equipment. If new development is needed to support an additional HSL section, for example, by introducing a different interface protocol instead of EULYNX SCI-CC, it will have an impact on the timeline. Development, testing, and commissioning will likely take longer compared to reusing the existing interface. The Cluster hardware often does not require an upgrade in such scenario, but new network equipment may require depending on the project scope. The data for new track-sections can be imported into system with no impact to live environment. Our company prefers machine-readable, validated data formats for all the infra related information as it significantly reduce the effort to import and test the data in the TMS system before commissioning. | Yes, “XXX” has capability to communicate with TMS from other vendors. Often this interface is specified according to customer requirements and needs. Once requirements are clear, a common agreed protocol to exchange the specified messages can be defined and implemented. | Source codes are part of Supplier intellectual property rights and shall be kept on the sole ownership of the Supplier. TMS systems are developed through large-scale product development projects. These projects demand extensive engineering expertise and deep technical knowledge, specialized resources and experience from traffic management systems. Building a new TMS system is based on existing code together with new development for the case specific features and other specific application modifications. The source code of the full TMS system is based on the same generic product code as other TMS systems in use by other customers. That source code cannot be given to any customer alone. Supplier is the only owner for the source code who can also maintain the source code and further develop that to respond the future requirements for the system. Supplier can also provide the support and maintenance for the installed system for an extended period when having the full control of the source code. In case the Supplier would cease to support the installed TMS system, the Supplier shall be responsible to provide the source code to the customer according to terms and conditions of a separate Escrow agreement. Escrow agreement does not pass the ownership of the source code to the customer, but it gives the latest system source code to enable the use and life cycle support for the delivered system. The customer will in such situation have the right to keep on modifying the system code and continue the use of the system for a long time. | As explained in question 20, we don't see that a viable solution to provide source code for the customer. The support and maintenance of the system cannot be guaranteed if the ownership would be transferred to a third party. The knowledge and resources of the system will be lost, and the life cycle of the system will be decreased. | The installed TMS system shall be supported according to a separate Support and Maintenance Agreement. That agreements shall include 24/7 help desk for the users with technical support, incident resolving and problem-solving practices. Typically, also a regular cyber security update service is part of the Support and Maintenance Agreement. Further system development should be agreed case-by-case between the Parties as the development needs will only be clarified after the project implementation period. | The installed TMS system shall be supported according to a separate Support and Maintenance Agreement. This agreement describes the support services and sets the targets for a long life cycle system. Typically, these contracts are valid for the first five years and then with automatic annual renewal. The content of the services can be amended when mutually agreed. Pricing of the services shall be bound to an agreed labour force index. Our company has a long experience on long-term support and maintenance agreements with its customers. For example, our support contract with one infrastructure manager has been in force over twenty years and the contract has been annually modified to support the changes in the installed base and to face the constantly updating support requirements. | In case the Supplier would cease to provide support for the installed TMS system, the Supplier shall be responsible to provide the source code to the customer according to terms and conditions of the Escrow agreement. The customer will in such situation have the right to keep on changing the system code and can continue the use of the system for a long time. Life cycle support shall be provided by the customer technical team or can be outsourced by third parties. The Supplier may be required to provide knowledge sharing for a short period and enabling the customer or a named third party to use the source code for the life cycle support functions. In such case the customer would have right to use and further develop the source code, but the ownership of the source code would not be transferred to the customer. | In our experience, our customers can have multiple systems and solutions with different technologies. Often these systems have different life cycles and may have shorter upgrade cycles Our company always proposes to procure such solutions which supports open and secure standardized protocols to communicate with these systems. “XXX” being a modular and upgradable solution is fully capable to support any new open standard/ protocol as part of the operational system. The “XXX” can be interfaced and enhanced at any time with the new systems obtained by our customers. | The EU legislation for Cyber security, including the NIS2, CSA and CRA (among others), forms an important legal framework for all systems and products used for serving critical infrastructure. Our company has been working these matters already for long and created internal capabilities to comply with all current and future Cyber Security needs. Our company is certified for ISO27001, and we are developing all new products to also pass the coming ENISA defined certification process in ‘Critical Product’ category, mandated by CRA. Additionally, our design processes for complying the national implementation of NIS2 is currently compliant in one country. Obviously our company needs to verify compliance with Czech law (Act No. 181/2014 Coll.) when going forward. | The Identity and Access Management (IAM) module manages all the users and their rights. The IAM solution can interface with Active Directory, for federated authentication, as long as the the proposed AD does not violate the Cyber Security Requirements of the system. Since the company´s IAM solution uses modern technology, the communication with AD, using ECDSA based keys is possible and even recommended, over the older RSA keys. Our company recommends updating the list of supported algorithms and certificates as part of cyber security management as vulnerabilities may be identified by authorised personnel during the life cycle of the system. | Yes, it is feasible and also essential to collect all the TMS log data in the customer’s own central logging system. This provides valuable data for our customers to build better insights about the infrastructure use, resource management and the system’s operations. Log transferring can be done with using industry standard protocols and practices. | Our company´s approach to high availability is based on hot-standby geo-redundant architecture. In this approach two fully functional geo-redundant TMS systems (Active and Standby) are operational. The Active site is chosen based on customer defined criteria while Standby site is processing all the data but not allowed to manage the traffic. Standby site is constantly synchronizing the operational data from Active site so that in case of switchover the operations resume from the same state. In practice, this means that Hardware, Software/applications, and network resources are duplicated on each level. 1. Fault tolerant, redundant Hardware clusters located in two different geographical sites. Failure of any hardware components at one site do not impact the availability of system. 2. Redundant software architecture where system monitors TMS applications and ensures that they are always up and running. 3. Networks and related topology are designed to ensure that a single fault in the data network do not impact the availability of the system. A Traffic Management System is considered a critical system in Rail Traffic Operations so availability figures of 99.99% are often required by infrastructure managers. For HSL, the value may be lower as currently it is communicated that HSL will be a commercial operation between specified time in a day. | "XXX" is designed in a way that any failure in the system hardware, application, operating environment, power outages is tolerated. In the above scenario, the system allows immediate takeover of the activities by other workplaces, in the same control room or in the geo redundant control room. "XXX" system uses the concept of “Control Roles”. Traffic Operator personnel who have rights for a specific “Control Role” can use any available PTD workstation to manage the traffic. The “Control Roles” can be managed by system admins. They can be shared or handed over to other traffic operators. A Traffic Operator using PTD can choose to activate a “Control Role” quickly with a single command, if required, in the same control room or in other control room. | "XXX" ensures the fault tolerance both on Hardware and Software level using hot standby geo-redundant architecture. The Hardware fault tolerance is done using cluster hardware (3 Nodes, Fault tolerant Storage and network equipment) to ensure any fault in hardware components can be tolerated. In addition, geo-redundancy of the clustered hardware provides additional layer for fault tolerance and availability. In the software/application level "XXX" is build using microservices and implement functionality in layers. In case of a fault in one signalling system (communication or other fault) the remaining system keeps working without any impact on the other areas and operations. | Yes, we have the expertise and capability to design and implement traffic control rooms that are fully compatible with your Traffic Management Concept and functional requirements. Our team is committed to deliver previously approved design solutions that meet your specifications in full. | In general, current HSL line controllers’ workplaces division proposal corresponds to the controlled line lengths and operational staff number. We have noticed that TCC Prague common controlled line length and number of controlled turnouts is almost double amount of TCC Prerov. In case of TCC Prague is in the down state (as an example, in case of power failure), it could be challenging to control complete HSL from TCC Prerov. We assume that "VRT Visocina 1" could be part of TCC Prerov "south section", and adjustment to the number of workplaces to be done accordingly during detailed design phase. | For the smooth efficiency, Line/Operational controllers should be able to takeover control of single or multiple lines on same workplace. Structure of control positions could be amended with an ETCS/Telecom monitoring workplace (one for each TCC). Adjustments could follow based on findings during the staff trainings in simulated environment. During detailed design, selected number of workplaces should comply with the worst-case scenario. | As it was answered to Q3.2 - "VRT Visocina 1" could be the part of purple line. Possible optimisations to be accessed during detailed design phase. | The currently proposed staffing for HSL control is sufficient to ensure all necessary activities are effectively conducted. Additionally, we are proposing: ETCS/Telecom monitoring role and clearly defined crisis management role (emergency and incident handling, one for each TCC). | This questionnaire provides good high-level information about the planned activities for the TMS Control Layer system. However, in such a large project it would be extremely important to open the full procurement plan about all related high-speed line activities that have interfaces or any relation, technical, commercial or schedule-wise, to this TMS project. Therefore, the full signalling and traffic management system should be explained in a clear and concise manner to scope out each project deliverables and main milestones with a clear reference to the neighbouring projects. After receiving the RFI answers we would encourage the customer to organize more detailed workshops, mutual discussions, and market dialogues about the planned activities. This would enable suppliers to provide most streamlined solutions and discuss about the technical definitions of all the external systems and their interfaces which are not part of the TMS Control Layer. In the final RFQ we ask the customer to reserve sufficient time for questions and clarifications. The more clearly stated requirements and project scope the better offers can be provided.
6 | XXX | This will strongly depend on the final architecture and requested functionalities of the project . | The proposed timeline is feasible if an existing solution, based on already existing subsystems, is going to be used (with a minimum of adaptions). In case a new development is requested the timeline (depending on the complexity of the newly developed product) is too optimistic. | Please refer to Question 2. | The proposed architecture is feasible. | The shown subsystems for the Control Level can be integrated into the solution. Additionally, there would be the possibility to add a module for staff management to the solution, which would help optimizing the staff planning. | For connections from the TMS to IXL/ SCWS à SCI-CC / Eulynx; for connections from TMS to neighbour TMS à TSI - TAF/TAP | It strongly depends on the operational concept of Správa železnic | Yes, we can define a protocol together with Správa železnic. Some parts will be covered by SCI-CC, others may have to be added as enhancement. | By using a defined set of commands and messages based on SCI-CC the interoperability will be handled. | <no answer> | If there is a possibility to use an existing solution which fulfils the requirements, developing a completely new system is not recommended as the investment costs (time & budget) will be much higher | The solution for the HSL TMS would be based on the following key points: EuLynx SCI-CC Interfaces TSI2023 TAF/TAP to RNE ATO GoA2 according to TSI2023 with interworking ERTMS BL4.2 or newer ERTMS BL 4.x or newer Web-UI Cyber-Security according EU Regulation CRA (2024-10) Reuse of our existing systems which have already proven their capabilities on HSL and could fulfil the requirements with adaptation and configuration. The adaptation of our requirements depends on how Správa železnic want to perform operations. It has to be well defined and clarified. | The mentioned requirements for the TMS can be fulfilled | As a single contractor, we are able to provide the complete solution. | Yes | Worldwide customers, however based on your general information we would offer solution based on our TMS system in a specific european country. | Yes, it is possible | The connection of another HSL section should be based on the same solution in order to optimise the integration by using a defined set of functionalities and interfaces. Details about timing and financial aspects should be part of the tender. | If the functionality and communication protocol/interface is well defined between the manufacturers it is possible. However, this strongly depends on the system and interfaces used in both countries (e.g.TSI TAF/TAP) | This information is manufacturer specific and confidential. | This information is manufacturer specific and confidential. | This strongly depends on the requirements and framework conditions. Based on this we can define what kind of support (maintenance) and additional development is required within which period of time. | Technological and industrial standard/norms have a direct impact on the product lifetime. We do offer long-term support for warranty and maintenance, which must be defined in the framework of the project | <no answer> | <no answer> | please refer to Question 12 | Yes | Standard logfiles can always be provided | The high availability is an essential part of our product solution and has a proven track of success. | This is possible due to the geo-redundancy feature of the solution and workplace redundancy | <no answer> | The traffic control rooms can be designed and implemented accordingly. | This depends on the way Správa železnic is currently performing operations and the grade of automation reflected in the actual solution. | The structure is feasible, in terms of efficiency it will depend (as mentioned in the answer for the question above) on the way Správa železnic is performing operations | This relates to the questions above. | This relates to the questions above. | The questions in the previous chapters gave a good insight on how the new TMS is intended to operate and what Správa železnic would like to achieve with the system. However, the actual requirements would be needed in order to evaluate how the solution could be set up. Generally everything seems feasible and manageable and could be covered by products which are existing in our portfolio.
7 | XXX | The price depends very much on the requested final functionality, interfaces and architecture. At this point we cannot provide an indication of price range. | The proposed schedule seems reasonable. The final confirmation depends on the necessary developments to comply with the requested specifications. | Will be provided in a later stage. | We agree with the proposed architecture since it can be implemented for the TMS. However, there are relevant factors that should be consider at the time of architecture definition and design. A major important factor under our vision is the scalability of the system with minimum impact. Another important component is the capability of integration of the different subsystems and workplaces that form the complete TMS system. Bearing that in mind, the introduction of one integration layer implementing open and standard interfaces, and that enables a smooth scalability and expansion of the system without or with minimum affection to the production systems is our proposed solution as architectural framework. This integration layer can be also based on ERJU initiatives int terms of communication protocols and data formats, what will ease the integration tasks for other systems. Therefore, the proposed architecture looks like in the following picture. The Digital Integration Layer itself may act as the DOSTI server and a gateway for the external systems when it comes to that. It is important to understand that the picture reflects the logical architecture. From the physical equipment point of view, the complete system is deployed over a clusterized platform so there are only one set of servers for the complete TMS system. Workplaces are based on thin clients what reduce the environmental impact into the control room and allows a smooth maintenance of the TMS equipment. | Our solution for TMS covers all the subsystems specified in the figure. Notwithstanding that the subsystems and architecture is supported it is noted that usually the Electric Control System is not included as part of a TMS solution in most of the railways administration but as a separated system, letting the TMS functionality taking care of the traffic and signalling systems. However, it is also important to remark that the contribution of the electric Control System to the traffic is getting more importance every day, especially with the introduction of ATO technology in the HSL and ETCS standards. This results in a better use of the energy and therefore costs savings and carbon footprint reduction. Another subsystem that is usually included is the Planning System. TMS needs for the automation tasks a planning system that is usually created offline according to line capacity and passenger demand. Then, the TMS adjust the schedule according to the real situation, avoiding, detecting and solving traffic conflicts taking into account also trackworks and speed restrictions. Our question is whether or not that Offline Planning System should be included in the procurement as part of the TMS or as an external system provided by others. Our company system support both approaches. | Eulynx let the door open to local, country specific, implementations. Our company has experience in those adaptations to specific railway administrators and national rules and standards. From that experience, national adaptations will be likely needed and also advisable in some specific cases. The proposal should be to use Eulynx protocol for the project, assuming also that the signalling (interlocking and RBC) provider(s) have Eulynx implemented in their systems. | Eulynx let the door open to local, country specific, implementations. Our company has experience in those adaptations to specific railway administrators and national rules and standards. From that experience, national adaptations will be likely needed and also advisable in some specific cases. The proposal should be to use Eulynx protocol for the project, assuming also that the signalling (interlocking and RBC) provider(s) have Eulynx implemented in their systems. | In the case that Eulynx protocol were not decided for this project, our company has the capability and experience to implement different kinds of protocol and to adapt the TMS to the Executive Level protocols. This has been done in the past for different European HSL projects. From that experience we can adopt any kind of protocol in the case that that would be necessary. | Our company has a wide experience on connecting signalling systems from different suppliers and with different kinds of ATP solutions. Typical process for compatibility is defining and align the communications protocol, design the set of indications and commands to be exchanged (messages comprised the interface), set of elements and finally, testing. The protocol might be one specific protocol in the signalling system, usually legacy systems or unable to implement standard protocols such as Eulynx or can be a standard protocol. Our TMS has available a set of specific and standard protcols (Modbus, OPC-UA, IEC-401 and IEC-404, Eulynx) to connect with the signalling system. | Yes, as stated previously we have a lot of experience in the communication and integration with different signalling systems. Besides our company, there are several references where we have integrated with other signalling manufacturers, both for Interlocking and ETCS. Below some examples are included. <not specified for anonymity reasons> | This depends on several parameters such as length and complexity of the installation, availability for testing or external works necessary for the TMS development. To improve the time to succeed, our company usually takes advantage of simulation of the signalling principles and Digital Twin solutions. This approach allows to minimize the necessary time for testing on field and reduce the number of uncovered errors to a minimum for the tests on field and commissioning. Having said that, typical time for TMS development and commissioning is around 4 years, bearing in mind the dependences from civil works, signalling and/or other external systems. | In our experience, TMS solutions are quite customer specific. Therefore, some adaptations would have always to be done, especially in terms of interfacing. Nevertheless, our system is based on open architectures and is tested and currently commissioned in more than 20 countries and highly customizable, so if we were to a ready-make solution where an alignment and convergence of requirements need to be achievable, that process would be much more smooth than with any other ‘closed’ system. | “XXX” is a system that may run in total automatic mode, under an ‘exception-based concept’. That means that the system can execute the planning present in a timetable, adapting the theoretical timetable to the operation conditions and current situation of the traffic and solving conflicts. From this concept, the operator only must intervene when something unexpected arises from the planning raises during the normal exploitation (exception) or because of planning works. The system loads one theoretical timetable with the planning. This timetable can be external to the system or included into it as part of the additional tools to be consider. Of course, the operator can intervene manually in the planning as it is needed. The system is being already used as a fully automated system in unmanned solutions for Automatic Train Operation. Compatibility with the different levels of ETCS, is one of the main features of the system and one of the major drivers for evolution. Currently the system is installed in several ETCS L1 and L2 projects and it has in the roadmap the adaptation and migration to hybrid train detection and ETCS L3. That is planned for 2027. The system is redundant, with a estimated rate of 99,999% of availability. The configuration in cluster provides 1 out of n availability, being n the number of servers. It supports also geographical redundancy with both cold and warm switchover from one centre to the other. In terms of scalability, the system is suitable both for small and large installations with projects already commissioned managing more than one hundred interlockings, for example. The system also supports distributed architecture, so new nodes can be created and incorporated to the system in case of necessity without prejudice of the performance and in a total transparent way for the user who will perceive the whole system as only one from a user interface perspective. As stated before, the system has been commissioned interfacing with different signalling suppliers (see paragraph 10 for details). Besides that, Eulynx protocol is being implemented to interface with both RBC and Interlocking as per the European standard of interoperability. The system stores all the events for different purposes: audit, playback, training and simulation… All the events are then stored in the hard disk in different formats according to the eventual purpose and the way of recovering. Reports can also be generated from the stored information; these reports can be customized by the user according to their needs. The period stored depends on several factors, such as the format or the number of records or events up to the capacity of the system. Scripts are configured to perform back up copies of the information which can be extracted by different techniques. The system fulfils Security Level 3 according to IEC-62443. It also will be compliant with the EU Cyber Resilience Act due to Novembre 2027. There is a complete suite of IT protection tools that are incorporated to the environment where the system is running providing in such way a complete resilient environment for the whole system. These tools consist of (non-exclusive list): • Access control, including double factor authentication • Remote software update • Network monitoring and intrusion detection • Super secure operating system Besides that, the communication system and equipment performance can be monitored using SNMP standard protocol. | The TMS system will be developed, engineered and commissioned by our company. Main external parts are HW components based on COTS HW. | Within our portfolio exists a technical solution (but not installed so far). The solution is based on a portable device, which allows to block track sections, temporary speed restrictions and commands to the TMS system. | We would recommend a broader range of 10-15 years to reflect better the installed base. | “XXX” may include at customer discretion (customizable function) Track Warning System functionality. This is implemented using handheld terminals allowing the maintenance staff to ask for permits and the necessary track protections in coordination with the Control Centre and operating the interlocking and RBC accordingly to introduce speed and track restrictions. The system can also connect to an external SCWS by means of a safe communication protocol. | This depends very much on the availability of an agreed interface protocol/ format. It is difficult to estimate a general number without further details. We would recommend the SCI-CC Eulynx interface or an already established interface as described before. | Yes, the TMS has been connected to adjacent TMS in HSL in two countries. For this connection, a specific protocol to exchange information at borders, such as train numbers or element status can be used. The system may incorporate an Enterprise System Bus (ESB) or Digital Integration Layer (DIL) to share information among different consumers. All the business data are present in the DIL so any system (not limited to adjacent TMS) with the appropriate rights and protection can exchange data with the TMS by using the DIL. The DIL can adapt to any message format, including Europe’s Rail Joint Undertaking (ERJU) specifications and has also capabilities to combine data so it can provide a more elaborated information from the published data. | Our company will provide the Source Code only to an Escrow Agent under defined conditions (e.g. providing access in case of bankruptcy of our company etc.). The source code is our key intellectual property and will therefore not be sold. | Our company will not sell the source code, but can offer a license agreement to transfer engineering know how to use the engineering tools for further adaptations/ use of the product. | The development will depend on the specification. A clear milestone for the requirements freeze should be included in the contract. The development phase (depending on the final requirements) typically will be between one and two years. | Provozujeme jeden TMS, který je přizpůsoben potřebám našich různých zákazníků. Všechny naše systémy jsou postaveny na sdílené platformě General Application (GA). Tato GA vrstva bude sloužit jako základ pro pokračující vývoj v rámci programu ERTMS v jedné evropské zemi v následujících 15 letech a pro jeden systém metra v následujících 25 letech. Pro zajištění pokračující podpory a kompatibility s dodavateli hardwaru vyžaduje systém minimální údržbu, především zahrnující výměnu hardwaru každých 7 až 10 let. Podle našich zkušeností následující klíčové faktory určují životnost TMS systému: Životní cyklus hardwaru – Dostupnost a podpora komponent COTS hardwaru, typicky 5-7 let na generaci. Operační systém a softwarový stack – Podpora dodavatelů pro distribuce "XXX", bezpečnostní záplaty a kompatibilita s aktualizovaným middleware a runtime prostředími (typicky 5-10 let na hlavní verzi). Evoluce hardwarové/softwarové architektury – Schopnost migrovat napříč hardwarovými a OS architekturami (např. z 16bitových na 32bitové na 64bitové platformy) pro prodloužení funkční životnosti. Požadavky kybernetické bezpečnosti – Schopnost splnit vyvíjející se standardy a praktiky kybernetické bezpečnosti po celou dobu životnosti systému. Provozní požadavky – Pokračující soulad s funkcionalitou řízení dopravy, integracemi a regulačními změnami. Podpora dodavatele a komunity – Dostupnost odbornosti, náhradních dílů a služeb podpory v čase. Úspěšně jsme podporovali podobné systémy více než 20 let, spravovali migrace z RTE, RTE-A a Unix na Linux napříč více generacemi hardwaru, přičemž jsme udržovali provozní kontinuitu po celou dobu. | To be discussed in a later stage. | The proposal is the use of the Digital Integration Layer (DIL) to exchange information among different systems. DIL is a framework to exchange messages using "XXX" event streaming platform as the main message broker but being able to adapt to other protocols for legacy or existing systems. By means of this Integration Layer the information is published and consumed by the different systems who subscribe to those data they are interested in. For the publisher system the number of subscribers and the constitution of data consumed are indifferent so the interface is unique what results in a simpler way of communication both for implementation and maintenance. | TMS system fulfils with the IEC 62443 standard Security Level 3 for Cyber Security. It also will be compliant with the EU Cyber Resilience Act due to Novembre 2027. See paragraph 13 for further details. | Yes, the system supports the connection to Active Directory and the use of SSL certificates. | Yes, the system can connect to any Business Analytics, Maintenance Management System or similar for logs collection and alarms and events propagation. Supported SPLUNK protocols are also supported by TMS. | 100% | TMS has the capability of geographical redundancy. Any workplace at any centre can take the control of the area controlled by other in case of failure or for task assignment strategy. Workplaces in both centres can be connected to the online server, so the switchover is immediate when the failure occurs. It is simply to take the control of the affected area from the other workplace. | Fault tolerance is ensured by the total system availability. All the servers are redundant at every centre. Geographical redundancy is also present between centres. If the online server fails, the workload of the server is transferred to the equivalent in the same centre. If all the servers in the online centres go down, the control is taken from the backup centre. This switchover between centres can be configured as automatic or manual, depending on operation condition (presence or not of staff at backup centre). | It is not within the core competence of our company to design and implement the traffic control rooms. Therefore, we would recommend to contract a local designer who is used to the local requirements. | Our company´s system with smooth operation, allows to reduce significantly the amount of operators/ working places. | Based on our experience the control workplaces can be reduced to an optimized amount. | The traffic management system could be centralized in one main facility with one backup system in case of emergency, if the communication system allows that. | As mentioned before, based on the high degree of automated operation, we see some room for improvement to reduce staffing/ workplaces. | Our company would recommend to have a specific discussion also about the required functionalities, architectural design and technical specifications before the tender will be published.
8 | XXX | Total budget of the project is related to many factors including but not limited to: Functionalities and subsystems included. Final level of Scope of Supply. Numbers and types of foreseen subsequent activations. Final level of redundancy required affecting also architecture. Number and level of interfaces with other signalling systems (with consequent protocols to be developed). Interfaces by means of standard/non standard protocol with external systems (e.g. data logger). Final set of Cybersecurity constraints. | Regarding the proposed schedule outlined in Appendix 4 for the TMS project implementation, we generally concur that the timeline appears feasible for certain aspects. However, we have some reservations concerning the 24-month timeframe allocated for the complete implementation of the first milestone. Specifically, we anticipate that the documentation, development, and validation of critical interfaces, such as EULYNX and ATO, will likely require a more extended period to ensure thoroughness and accuracy. These integrations are complex and necessitate rigorous testing and validation processes to guarantee seamless and reliable operation within the broader railway system. Therefore, while the overall schedule may be achievable, we suggest a closer review of the timeline for Milestones, potentially extending it to better reflect the realistic complexities involved in these crucial interface implementations. We would be pleased to provide more specific suggestions for schedule modifications once we have a deeper understanding of the detailed activities and dependencies within each milestone. Concerning the approximate percentage distribution of the total project amount across individual milestones, we are able to provide an indicative breakdown. However, this would be most accurate after a more detailed analysis of the resource allocation and effort required for each stage. We can certainly offer a preliminary estimate based on our current understanding and refine it as the project progresses and more detailed planning is completed. | See the above considerations. | Regarding the architecture presented in Figure 3 for Procurement: TMS Control Level for HSL, as outlined in Appendix 2, we find it to be generally acceptable. However, a thorough evaluation should continuously consider the evolving landscape of European specifications, particularly with respect to the System Pillar directives and requirements. Considering our collective involvement in the System Pillar standardization efforts, we have a few observations. Regarding the proposed architecture in Figure 3, while it outlines the interconnectedness of various systems, we see some areas that could be refined to better align with typical TMS scopes and functionality: Inclusion of ATO, PED, DOSTI, and PDŽDC within the TMS Control Level: Typically, a TMS focuses on high-level traffic planning, monitoring, and control. Systems like Automatic Train Operation (ATO), Power Electric Distribution (PED), DOSTI, and Railway Infrastructure Controllers' workplaces (PDŽDC) are usually external entities that the TMS interfaces with, rather than being integral modules within it. ATO Trackside: The diagram shows the ATO System interacting via CoreNET. In standardized railway architecture, especially considering ERTMS/ETCS deployment, the trackside ATO functionality should ideally reside at a similar level to the Radio Block Centre (RBC), managing train movements based on signalling and potentially higher-level commands from the TMS. The current representation might not clearly reflect this hierarchical relationship. | Referring to the architecture in Figure 3, our standard core TMS solution encompasses as a minimum the TMS Server and the PTD (Line controller's workplace). These are the fundamental components that enable traffic management, planning, and real-time monitoring functionalities. Even if our standard TMS focuses on these central elements, since the figure illustrates various interconnected systems, and we recognize the value of a comprehensive solution, we can also provide, but not limited to, the diagnostic and maintenance subsystems. | Adhering to international and European railway communication standards is crucial. Specifically, leveraging protocols like ERTMS/ETCS standards where applicable, and exploring emerging standards within the System Pillar directives and requirements, would provide a common language for data exchange. For more generic data exchange, widely adopted IT standards such as XML or JSON for data formatting, coupled with secure and reliable communication protocols like IP-based networking with TLS/SSL encryption, would be highly beneficial. Furthermore, defining standardized Application Programming Interfaces (APIs) based on these protocols would be the key. These APIs would act as well-defined gateways, allowing the TMS to request and receive data from the signalling systems in a consistent format, abstracting away the proprietary details of each manufacturer's equipment. | Our approach to adapting the EULYNX SCI-CC specification for the Správa železnic / HSL environment is focused on ensuring both adherence to the standard and seamless integration within the specific context of this project. Firstly, we recognize the ongoing evolution of the SCI-OP protocols within the System Pillar working group. Therefore, our strategy involves a continuous monitoring of these developments to ensure our implementation remains aligned with the latest advancements and recommendations. This proactive approach allows us to incorporate any necessary updates or modifications throughout the project lifecycle. Secondly, a key aspect of our adaptation strategy involves a thorough verification of the adherence of all involved suppliers to the EULYNX SCI-CC specification. This includes rigorous testing and validation processes to confirm that the interfaces implemented by different vendors are compliant with the standard. This step is crucial for ensuring interoperability and the smooth exchange of command and control information between various subsystems within the HSL environment. | We are certainly capable and willing to collaborate closely with Správa železnic to define this communication protocol, taking into full account the timelines associated with the first HSL launch date. Our company possesses the necessary competence to develop this protocol, drawing upon our established experience in successfully interfacing with both one country RBC and Interlocking systems, moreover we are implementing a solution to interface the "XXX" RBC and Interlocking. This prior experience provides us with a strong foundation in understanding the specific requirements and complexities involved in such integrations. | To guarantee the openness and seamless integration of the TMS with signalling systems from different suppliers, we will maintain a strong commitment to adhering to evolving European directives and the System Pillar directives and requirements. Our strategy involves incorporating a dedicated integration and communication layer within the TMS architecture. This layer will be designed with the inherent flexibility to accommodate various communication protocols and data formats. Furthermore, this layer will provide the capability to develop and integrate customized interface modules as needed to specifically address the unique characteristics of different signalling system manufacturers. | Our TMS can interact with RBCs and interlockings provided by any interlocking and other TMS suppliers for all European lines by means of standard protocols set-up by the European Union. At the moment we already have in commercial service integration with "unnamed companies". | Development timeframe strictly depends on what kind of functionalities and requirements are included in the final specification: estimated maximum timeframe 3 years. | If we were to recommend a ready-made TMS solution without significant development, our proposal would likely be based on a system that has been successfully deployed within one European country railway signalling environment. Such a system offers a comprehensive suite of functionalities for traffic management, planning, and control, benefiting from proven operational experience and established interfaces in a market were important Signaling supplier already operates and interacts. However, to adapt this ready-made solution to your specific requirements for the Správa železnic / HSL environment, several key areas would need careful consideration and potential adjustments: Signaling System Compatibility Integration with Existing Systems Operational Procedures and Workflows Language and Localization. It's important to acknowledge that while a ready-made solution offers the advantage of faster deployment and potentially lower initial costs, some level of adaptation and configuration would almost certainly be required to fully meet the specific requirements of the HSL project. The extent of these adaptations would depend on the degree of difference between the signalling system, existing infrastructure, and operational practices compared to the environment for which the ready-made solution was originally designed. Furthermore, it's worth noting that we are also actively developing TMS solutions for international projects. These solutions are being designed with flexibility and adaptability to minimize adaptions for specific Customer needs. | Regarding the minimum requirements for TMS outlined in paragraph 3 of Appendix 2, we generally do not foresee significant difficulties in implementing the requirements that are strictly within the scope of a Traffic Management System. However, our initial review suggests that some of the listed minimum requirements might extend beyond the typical functionalities and boundaries of a core TMS. To ensure clarity and a focused approach, we believe it would be beneficial to distinguish between requirements that are inherently TMS-related and those that pertain to interfacing or integrated systems. | Our proposal focuses on delivering a core TMS solution developed and supplied primarily by us. This includes the central TMS Server and the PTD (Line controller's workplace) software. For the underlying hardware infrastructure required to run the TMS, we typically utilize commercially available, off-the-shelf components. This approach offers benefits in terms of cost-effectiveness, vendor flexibility, and ease of future upgrades or replacements, mitigating risks associated with proprietary hardware lock-in and potential obsolescence. Regarding the interconnected systems illustrated in Figure 3 (such as ATO, PED, DOSTI, PDŽDC, and potentially the diagnostic system), to ensure maximum flexibility and ease of configuration within the overall HSL environment, we may propose integrating solutions from other specialized suppliers or trusted partners. This collaborative approach, where if required we can act as an integrator, allows us to leverage best-in-class expertise for each specific subsystem and ensures seamless interoperability through well-defined interfaces. | As a company we had the opportunity to work with TWS supplier, the collaboration was primarily related to projects where we acted as a turnkey supplier for the wayside plant. We have also been involved, being a computer based interlocking supplier, on some feasibility studies led by one European infrastructure manager for interfacing TWS systems to interlocking. | As a TMS supplier, we have in service systems which independently of the first moment of go-live to commercial service, are continuously modified due to layout configuration and upgraded in terms of functionalities required from the Customers. In the last 7 years, we have been working on TMS managing more than 100 stations for different Customers and we have in progress 7 NEW conventional lines and a new High-Speed Line. Please note also that as "XXX" we have been turnkey leaders for High Speed Lines in some "specific listed projects" | Yes, it is indeed possible to supplement our TMS with information originating from an SCWS-I (Signal Controlled Warning System with Interface). Our TMS architecture is designed to be open and interoperable, allowing for the integration of relevant data from various railway subsystems to enhance situational awareness and operational efficiency. The primary way our TMS would interact with an SCWS-I would be by receiving and processing information related to trackside warnings and safety statuses. This data could then be visualized within the TMS interface, providing operators with a comprehensive view of the operational environment and potential hazards. This information could be valuable for traffic planning, conflict resolution, and real-time adjustments to train movements, ultimately contributing to safer operations. However, it's crucial to clarify the boundaries and responsibilities regarding safety-critical control actions. While our TMS can consume and display information from an SCWS-I, the direct safety-critical interfacing and control logic for such a system should appropriately reside within the interlocking system or other dedicated safety-critical layers. The interlocking is the designated system for enforcing safety rules and directly controlling trackside elements based on signalling and safety interlocks. | Estimating the financial and time requirements for connecting another HSL section to an already functioning TMS system is contingent on several factors, primarily the size and complexity of the new section being integrated. Larger and more intricate sections naturally entail more extensive configuration, testing, and validation efforts, which would influence both the cost and the timeline. We would approach this integration with a strong focus on minimizing disruption to the existing operational service. Our planning prioritize methodologies that allow for the connection of the new section with the least possible impact on ongoing traffic, aiming for seamless integration and a smooth transition. This might involve phased implementation, parallel testing environments, and cutover strategies designed to maintain service continuity as much as possible. The format of the data provided for implementing the new section has a significant impact on both the time and financial requirements. In line with EULYNX specifications already in exercise and the European and System Pillar directives, we strongly prefer standardized data formats that promote interoperability and data consistency across railway systems. Adherence to EULYNX data exchange formats, to European and System Pillar directives, would significantly streamline the integration process. These standardized formats ensure a well-defined structure and semantic clarity, reducing the effort required for data mapping, validation, and system configuration. | Yes, it is indeed possible to connect our TMS with a TMS from another manufacturer, which could be particularly relevant for cross-border HSL connections. We have practical experience with such interoperability scenarios within one European country, where our TMS solutions are already interfaced with TMS systems from other major providers like "XXX" and "YYY" at a regional (cross-regional) level. These existing integrations demonstrate our capability to exchange relevant operational data and coordinate traffic management functions with other TMS platforms. Furthermore, we are actively involved in a Work Package of the Europe’s Rail project called "XXX", which specifically focuses on establishing standardized interfaces and protocols for cross-border TMS-to-TMS communication. This initiative aims to facilitate seamless data exchange and coordinated traffic management across different national railway networks, addressing the specific challenges and requirements of international rail connections. | Regarding the requirements for long-term sustainability and flexibility of the TMS solution, our standard approach does not involve the provision or sale of the complete system source codes. This stance is primarily due to the protection of our intellectual property rights, which represent significant investment in research, development, and innovation. The source code is a core asset that underpins the unique functionality and competitive advantage of our TMS solution. However, we understand the importance of long-term sustainability and the need for clients to have a degree of assurance regarding the future maintainability and evolution of the system. To address these concerns, we are open to discuss the establishment of a source code escrow agreement. Under such an arrangement, the source code could be deposited with a neutral third-party escrow agent. Release of the source code to the client would only occur under specific, pre-defined conditions, such as the cessation of supplier business operations or supplier failure to provide essential maintenance and support as contractually agreed. | Please refer to answer on the above point. | A useful first support would be a technical assistance (by means of a presidium through a skilled resource situated in the central operational control centre) during the first months of operations. A second kind of support would be in maintenance, with Customers having the first maintenance level within their organization (after a training path from the supplier) and the supplier the second and third level. This kind of support should be covered, in our view, with a first period of maintenance of 2/3 years priced in the main contract and, at the end of it, with biennial or triennial renewable contracts, to account for changing market situations related to prices. A third kind of support would be the availability of the Supplier to support the Customer with evolutive maintenance (Generic Application modification for the implementation of new functionalities). A fourth support will be in LCC (Life Cycle Cost) and obsolescence management field. | Several key factors, in our view, determine the lifetime of a complex system like a TMS, encompassing both technical and "moral" (or obsolescence-related) aspects. From a technical perspective, the initial design of the system plays a crucial role. A modular and well-architected system, built with open standards and clearly defined interfaces, tends to have a longer lifespan. Configurability and upgradability are also vital. A TMS that can be adapted to evolving operational needs and technological advancements through software updates and modular expansions can avoid premature obsolescence. The choice of hardware components is equally important. Utilizing Commercial Off-The-Shelf (COTS) hardware ensures easier maintenance and replacement over time, reducing reliance on proprietary or end-of-life components. From a "moral" perspective, the system's perceived value and alignment with current technological standards influence its lifespan. A system that becomes difficult to integrate with newer technologies or that no longer meets evolving operational demands may be considered obsolete, even if it is still technically functional. Our experience with long-term support for similar TMS systems demonstrates our commitment to ensuring extended system lifecycles. We have systems currently in operation for over 20 years, evidence to our focus on robust design, maintainability, and continuous support. Our approach includes: Ongoing Software Maintenance and Updates: We provide regular software updates to address bugs, enhance performance, and incorporate new features, ensuring the system remains current and aligned with evolving operational requirements. Dedicated Customer Support Services: Our dedicated support teams offer timely assistance for technical issues, ensuring minimal downtime and continued reliable operation. Long-Term Hardware Strategy: Our reliance on COTS hardware facilitates easier sourcing of replacement parts and allows for gradual upgrades to newer hardware platforms as needed, without requiring a complete system overhaul. System Evolution and Upgradability: We design our TMS with future evolution in mind, allowing for the integration of new functionalities and technologies to extend the system's useful life and protect our clients' investment. In essence, we believe a combination of sound technical design emphasizing modularity, configurability, and maintainable hardware, coupled with our long-term commitment to customer support and system evolution, are the determining factors in achieving a long and sustainable lifetime for our TMS solutions. Our track record with systems operating for over two decades underscores this commitment. | Our proposed approach to the long-term sustainability of our TMS solution is rooted in our commitment to providing continuous and reliable support throughout the system's lifecycle. While we understand the need for an exit strategy, our primary focus is on establishing a strong, long-term partnership with Správa železnic / HSL, ensuring that our expertise and support are consistently available. If unforeseen circumstances would prevent us from continuing to fulfil the terms of the service contract or if system support were to be terminated, we would implement the following mechanisms to facilitate a smooth transition of management and operation: Comprehensive Documentation: We will maintain thorough and up-to-date documentation detailing all aspects of the TMS, including its architecture, functionalities, interfaces, configuration, operation, and maintenance procedures. This will serve as a critical resource for any successor entity. Standardized Interfaces: Our TMS is designed with adherence to relevant industry standards and open interfaces. This approach facilitates integration with other systems and reduces reliance on proprietary technologies, making it easier for another vendor to potentially assume support and management responsibilities. Source Code Escrow (as previously mentioned): As outlined earlier, we could be in principle open to establishing a source code escrow agreement to provide an added layer of security for the long-term maintainability of the system under specific, predefined conditions. However, we want to underscore that our core strategy is focused on providing exceptional long-term support that negates the need for such an exit scenario. Our history demonstrates a strong commitment to our clients, with TMS systems supported by us for over two decades. We invest heavily in our support infrastructure and personnel to ensure we can continuously meet our clients' evolving needs. | To ensure seamless communication and data exchange between our TMS system and future communication systems from various manufacturers (operation applications, CCTV systems, information systems, etc.), we propose a technical approach grounded in adherence to evolving European directives, the System Pillar requirements, and widely adopted open IT standards. Our strategy centres on building robust and flexible interfaces that can accommodate a diverse range of systems. To achieve this, we will leverage the following technical solutions, standards, and protocols: Compliance with European Directives and System Pillar: We maintain a strong commitment to monitoring and adhering to the latest European directives and the specifications defined by the System Pillar working groups. This proactive approach ensures our interfaces are aligned with the evolving standards for railway data exchange and system interoperability. Core IT Standards: We will utilize fundamental and well-established IT protocols such as TCP/IP for network communication and HTTP/HTTPS for web-based data exchange. These protocols provide a reliable and widely supported foundation for system integration. Data Exchange Formats: For structuring and exchanging data, we will primarily employ open and flexible formats like XML and JSON. These formats are platform-independent, human-readable, and offer robust mechanisms for data modelling and parsing, facilitating easy integration with systems from different vendors. Standardized RESTful APIs: We will implement RESTful Application Programming Interfaces (APIs) based on open standards. RESTful APIs offer a lightweight and stateless approach to system interaction over HTTP(S), enabling straightforward integration for various applications. This will allow future systems to easily query and exchange data with our TMS in a standardized manner. Publish/Subscribe Services: To enable efficient and event-driven data exchange for real-time information dissemination, we will implement publish/subscribe (Pub/Sub) messaging patterns. This allows our TMS to publish or receive events and data without requiring constant polling. This approach optimizes network traffic and ensures timely data delivery. | Yes, we are fully aware of the critical importance of cybersecurity for ICT infrastructure, cable routes, and facilities within the railway environment and are committed to meeting the requirements outlined. We understand that these legal regulations mandate a high common level of security for network and information systems, encompassing measures for protection against cyber threats, incident handling, business continuity, and supply chain security. Our approach to ensuring the cybersecurity of our TMS solution and its associated infrastructure involves a comprehensive and multi-layered strategy. This includes: Secure Design Principles: We integrate security considerations throughout the entire lifecycle of our TMS solution, from initial design to deployment and maintenance. Compliance Verification: We will meticulously review all the specific requirements of the Czech Cyber Security Act and Decree, as well as the relevant EU regulations, to ensure our solution adheres to each provision. This includes technical and organizational measures. Risk Assessment and Mitigation: We conduct thorough risk assessments to identify potential vulnerabilities and implement appropriate mitigation strategies to protect the TMS infrastructure and data. Security Hardening: We employ industry best practices for system hardening, including secure configuration, access control mechanisms, and regular security patching. Incident Response Planning: We have established procedures for detecting, responding to, and recovering from cybersecurity incidents to minimize potential impact on operations. Security Awareness and Training: We emphasize the importance of cybersecurity awareness among our personnel involved in the development, deployment, and support of our TMS. We are committed to working closely with Správa železnic / HSL to understand their specific security requirements and to demonstrate how our solution aligns with the applicable legal and regulatory frameworks. We will provide detailed documentation and are prepared to undergo necessary audits and assessments to validate our compliance with the Czech Cyber Security Act, the Cyber Security Decree, and the relevant EU directives. Our priority is to deliver a secure and resilient TMS solution that meets the stringent cybersecurity standards mandated for critical infrastructure. | Yes, from our perspective, it is feasible for the proposed TMS system to support access control by connecting to Active Directory and, at the same time, secure communication using an SSL certificate issued by an internal Certification Authority (CA) with the ECDSA algorithm. Integrating with Active Directory is a common and well-established mechanism for centralized user authentication and authorization. Our TMS architecture can be designed to leverage standard protocols like LDAP or Kerberos to connect to your existing Active Directory infrastructure. This would allow for streamlined user management, where user accounts and access privileges are managed centrally, enhancing security and simplifying administration. Our TMS can be configured to utilize such SSL certificates to establish secure, encrypted communication channels (HTTPS) for user interfaces, API endpoints, and other network interactions, ensuring the confidentiality and integrity of data transmitted to and from the system. Whether the implementation of these specific features – Active Directory integration and support for internal ECDSA-based SSL certificates – is included as part of the standard TMS delivery would need to be clarified based on the specific requirements and scope of the procurement. These are functionalities that we can certainly evaluate and implement as part of the solution. We would need to understand the specific details of your Active Directory environment and the format/provisioning of your internal ECDSA certificates to ensure seamless integration and configuration. | Yes, from our perspective, it is feasible to ensure that the proposed TMS system can connect to a central system for collecting logs, such as SPLUNK. Integrating with external logging and monitoring platforms is a common requirement for modern enterprise systems, and our TMS architecture is designed to accommodate such integrations. We understand the importance of centralized log management for security analysis, system monitoring, and troubleshooting. Our approach to facilitating this integration would involve leveraging standard protocols and data formats commonly supported by log collection systems like SPLUNK. These may include: Syslog: A widely adopted standard protocol for message logging, allowing the TMS to forward system logs to a SPLUNK instance. HTTP/HTTPS with structured data: Logs can be formatted as structured data (e.g., JSON) and transmitted securely to a SPLUNK HTTP Event Collector (HEC) endpoint. File-based transfer: Logs can be written to local files in a defined format that SPLUNK can then ingest. We would need to understand the specific configuration and requirements of your SPLUNK environment to ensure seamless connectivity and proper log formatting. However, based on our experience with integrating with various monitoring and logging solutions, we are confident in our ability to meet this requirement. Integrating with a central log collection system like SPLUNK enhances the overall manageability and security posture of the TMS solution. | To ensure the high availability of the TMS system, we employ several key strategies designed to minimize downtime and maintain continuous operation. Firstly, we implement redundancy at critical component levels, including servers, network infrastructure, and data storage. This eliminates single points of failure, ensuring that if one component experiences an issue, a backup can seamlessly take over. Secondly, we establish automated failover mechanisms. These mechanisms are designed to automatically detect failures in primary systems and rapidly switch operations to redundant backup systems without manual intervention. This swift transition minimizes service interruption and maintains system availability. Thirdly, we incorporate continuous monitoring and proactive alerting. Our TMS solution includes comprehensive monitoring tools that track the health and performance of all critical components. We implement proactive alerting systems that notify our support teams of potential issues before they escalate and impact operations, allowing for timely intervention and preventative maintenance. Finally, we implement robust backup and recovery procedures. Regular backups of critical data and system configurations are performed, and well-tested recovery procedures are in place to ensure swift restoration of the system in the event of a major incident, minimizing data loss and downtime. Regarding system availability, we consider a value of 99.99987% to be a suitable and generally achievable target for the overall TMS system availability. This figure reflects our commitment to providing a highly reliable and consistently operational system. | To ensure immediate workplace takeover in the event of a system failure at one location, such as between the workplaces in Prague and Přerov, we propose a solution leveraging high availability with active-standby redundancy and automated failover. This involves deploying identical, fully synchronized TMS systems and the necessary supporting server infrastructure at both the Prague and Přerov locations. During normal operation, one location would function as the active primary site, with its workstations and servers handling all TMS activities. Simultaneously, the other location would operate in a hot standby mode. This hot standby system maintains a continuous, real-time mirror of all critical data, system configurations, and operational states from the active primary site. In the event of a system failure at the active primary site (e.g., Prague), an automated failover mechanism would immediately detect the issue and seamlessly switch operations to the hot standby site (e.g., Přerov). This automated process ensures that the TMS system at the standby location can take over all activities with minimal to no manual intervention and with near-zero downtime. Operators at the previously standby location would be able to resume their tasks almost instantly, ensuring the continuity of TMS operations without significant disruption. This active-standby redundancy model with automated failover provides a robust solution for immediate workplace takeover, guaranteeing high availability and resilience against localized system failures. The continuous synchronization of data between the active and standby sites is crucial for ensuring a consistent operational picture and a seamless transition during a failover event. | To ensure the fault tolerance of the TMS system, we employ a comprehensive, multi-layered approach integrating both hardware and software solutions. At the hardware level, we implement redundancy for critical components, including servers, network devices, and storage systems. This design ensures that in the event of a hardware failure, a redundant counterpart can immediately take over, maintaining system operation without interruption. We also utilize RAID (Redundant Array of Independent Disks) configurations for our data storage solutions. RAID provides data redundancy by distributing data across multiple disks, protecting against data loss and ensuring continued operation even if a disk fails. On the software side, we adopt a modular architecture. This design principle isolates different functionalities of the TMS into independent modules. If one module encounters an issue, it is less likely to cause a system-wide failure, limiting the impact of the fault. We also implement robust error detection and handling mechanisms within the software. These mechanisms are designed to gracefully manage unexpected situations, such as invalid inputs or communication errors, preventing system crashes and ensuring continued stability. Furthermore, automated restart capabilities are incorporated for critical processes. Should a transient software failure occur, these processes can automatically restart and recover without manual intervention. Finally, we utilize data replication and synchronization across our redundant systems. This ensures that critical data is consistently available and up to date on both the active and standby systems, safeguarding against data loss even in the event of a more significant failure affecting a primary component. By combining these hardware and software fault tolerance measures, we aim to create a TMS system that is highly resilient and capable of maintaining continuous operation even in the face of component failures or unexpected errors. | Yes, the design of control rooms is in our competencies so we are confident that we can implement traffic control rooms that will be fully compatible with your Traffic Management Concept (Appendix 3) and your functional requirements. Our approach to such projects involves a thorough understanding of your operational workflows, the roles and responsibilities of the personnel within the control rooms, and the overall objectives outlined in your Traffic Management Concept. We are experienced in designing ergonomic and efficient control room environments that optimize operator performance and situational awareness. This includes considerations for workstation layouts, information displays, communication systems, and the overall physical environment to support effective traffic management. In particular, numbers of operators per profile (line controllers, operational controllers, infrastructure controllers, and Electrical system controllers) are usually to be confirmed after an ergonomic study, taking into consideration the tasks analysis and allocation to the operators, alarms management, level of automatic functions, complexity and frequency of the train circulations, and external railways connexions. It is important to note that some functional requirements outlined in Appendix 3 might extend beyond the direct functionalities of the TMS software itself and may encompass aspects related to the physical control room infrastructure (e.g., furniture, large display screens, etc.) or integration with other external systems not directly part of the TMS. We are committed to fulfilling all requirements that directly pertain to the TMS and its interaction with the traffic control room environment. For requirements that fall outside the typical scope of a TMS but are crucial for the overall control room functionality, we are open to discussing potential solutions, including collaboration with specialized partners, to ensure a comprehensive and fully compatible solution that meets all your needs. | For CDP Prague, West Section: 2 line controllers for 2 line parts with a junction and a common part (80km and 35 km) seem enough, with one shared operational controller. One of these operators should surely also have to survey the ventilation of the VRT Středohorský tunnel, perhaps with a separated ventilation control system, not so much workload as often managed by automatic function, but he/she should be ready to act on it in case of appearance of alarms East Section: 3 line controllers (surely 1 for VRT Vyvhodni part 71 km, and 2 for longer part 217 km), one shared operational operator with west section seems also enough. For CDP Prerov South section: 1 line controller, similar to west Section of CDP Prague, 2 railway parts with a junction and common part (68 km + 30 km), without tunnel, 1 operational operator, common with north section, and if train traffic is little bit less important than west Section of CDP Prague, it seems enough. North section: 2 line controllers for one rail part of 139 km, with a shared operational operator with south section, seem also enough. Regarding the train traffic movements, there is also the function of offline timetable creation and updates. If it is included in the scope of the TMS control system, one additional operator would be necessary, but not 24 hours a day. For “Railway infrastructure controllers”, it depends on the precise role allocated to these operators: signalling maintenance alarms, work lineside possession supervision, isolation management, line side maintenance supervision, etc. If it is all these functions, 3 and 2 could be enough. For Electric system controllers, 3 for CDP Prague (about 400km), and 2 for CDP Prerov (about 240 km) seem enough. | Refer to answers to question 2 just above. The previous answer has been given with our past experiences. Please note that as Mermec group we have been turnkey leaders for High Speed Lines in some projects like for examples in "XXX": 110 km, mixed traffic (international trains, domestic trains, freights trains, 3 stations, 5 junctions to external railway lines): 2 line operators (signallers), 1 operation operators (supervisor), 1 infrastructure operator (maintainer), and "YYY": 183 km, mixed traffic (high speed and conventional trains), 3 stations, 2 line operators + 1 in spare, 1 operation operator (supervisor), infrastructure operator (maintainer). It should be also taken in consideration that areas of controls (also named responsibility zones) can be usually dynamically distributed to different workplaces, where areas of controls can be managed by a traffic controller at certain moment of the day, depending of the current traffic movements or when troubles or infrastructure unavailability should happen. | Yes, the division of sections seem to be logical. To give a more accurate advice, the frequency of train circulations, the usage of rolling stocks should be also considered, in order to try to optimise the allocation, mainly for the timetable management and for the regulation, delays management functionalities. | Refer to answers to question 2 just above. The activities tunnel Ventilation supervision and offline timetable creation and updates have not been found allocated to any operator. | In addition of what have been said above, in our opinion it should be included what below: Operational needs in term of number of trains per hours, Train circulations foreseen per type of trains (if applicable). For the back-up workplaces, which risks/failures need to be covered? Which functionalities need to be proposed, mainly for the automatic modules, for helping/supporting the operators in their activities?
9 | XXX | Our company estimates the total cost for the implementation of a comprehensive Traffic Management System (TMS) for high-speed lines in the Czech Republic to range between €20 million and €30 million. This estimate includes all key components such as software development and customization, hardware procurement and configuration, system integration with existing national infrastructure, as well as training and knowledge transfer to Správa železnic personnel. The final cost will depend on several key variables: • The degree of integration required with legacy systems and other railway operational platforms, • The level of hardware redundancy and failover capacity to meet desired availability targets, • Cybersecurity compliance efforts, particularly adherence to national and EU regulations including the NIS2 Directive and Czech Cyber Security Act, • The breadth and depth of the training program, especially the setup of a training hall and simulation-based instruction for various operator profiles. These factors will influence both the implementation timeline and the resource allocation strategy. Our company is prepared to provide a more refined cost structure once specific project constraints and expectations are clarified. | Our company supports the structure and intent of the proposed implementation schedule presented in Appendix 4. The progression from preparation and design through integration, pilot operation, and ongoing maintenance reflects a realistic and professionally staged approach suitable for a national-level TMS deployment. Based on our experience in similar international projects, we find the proposed durations reasonable. However, we recommend that key risk buffers be embedded between Milestone 3 (Integration and Testing) and Milestone 4 (Pilot Operation) to accommodate potential delays in third-party system integration and formal certification—particularly for interfaces requiring compliance with standards such as EULYNX SCI-CC and cybersecurity audits. Regarding financial allocation, our company proposes the following indicative distribution of the total project amount across the milestones (this distribution balances early development efforts with the capital-intensive deployment and post-commissioning support, and ensures proportional funding throughout the TMS lifecycle.): | Based on our experience with comparable traffic management system implementations, we propose the following indicative schedule for the TMS Control Level implementation for high-speed lines in the Czech Republic. This timeline integrates the milestones listed in Appendix 4 and supplements them with additional key activities essential to successful project delivery. Dependencies and Workflow Summary • Phase overlaps are critical: design activities (Milestone 1) and interface coordination (Milestone A) must begin immediately and run in parallel. • FAT (Key Milestone B) is a crucial quality gate before site deployment begins in Milestone 3. • Pilot operations (Milestone 4) rely heavily on stable site installations and completed staff training. • Post-Go-Live milestones (5–7) are dependent on the national rollout timeline and maintenance agreements. This schedule offers a structured yet flexible roadmap, enabling risk management through early testing, gradual deployment, and phased training. Indicative Project Schedule with Milestones: | Answer: Yes, our company generally agrees with the architecture outlined in Figure 3 of Appendix 2, which provides a layered and modular structure suitable for the deployment of a national-level Traffic Management System (TMS) Control Level. The separation between executive systems, control logic, communication layers, and user workstations mirrors industry best practices and aligns well with the architecture used in "XXX" TMS deployments in other European railway environments. However, based on our experience, we would like to highlight a few considerations and suggestions that could enhance the architecture and mitigate potential limitations: 1. Diagnostic and Monitoring Layer: the current architecture focuses on operational flow but appears to underrepresent system observability and health monitoring. We recommend explicitly integrating a diagnostics and performance monitoring layer to support real-time system analytics, fault detection, and SLA compliance. 2. Cybersecurity Layering: while the architecture reflects standard system components, we suggest a dedicated security management module, covering intrusion detection, endpoint protection, and secure access management. This is especially critical given NIS2 and Czech cybersecurity requirements. 3. Scalability and Modularity: the architecture should support dynamic scaling—both vertically (new functions) and horizontally (new lines or traffic control rooms). From our perspective, the use of containerized microservices and stateless modules (as implemented in "XXX") enables better lifecycle management and future expansion. 4. Data Interoperability: for long-term success, we emphasize the importance of standardized interfaces (e.g., EULYNX SCI-CC, FRMCS), and a clear governance model for managing evolving APIs. This ensures compatibility with future railway digitalization efforts and third-party systems. In summary, the proposed architecture is a solid foundation. With the above adjustments, it would offer enhanced transparency, resilience, and adaptability, qualities essential for the future-proof operation of the Czech Republic’s high-speed rail infrastructure. | Our company´s TMS platform fully supports the functional architecture presented in Figure 3 of Appendix 2 and can deliver all key subsystems identified within the TMS Control Level scope. Specifically, "XXX" includes and natively integrates the following subsystems from the diagram: • PTD (Planning and Timetable Development) • PDŽDC (Daily Traffic Management) • PED (Real-Time Traffic Execution and Dispatching) • DOSTI (Data Exchange Layer with Executive Systems) • JDK Proxy and Middleware Interfaces for IXL/ETCS Connectivity • TCS Workstations and Operator Interfaces • TMSNet and CoreNet Communication Infrastructure In addition to the listed components, "XXX" offers several enhanced and value-added subsystems that go beyond the baseline architecture and strengthen operational control and decision-making: • Decision Support System (DSS): Provides predictive traffic analysis, disruption simulations, and optimization recommendations. • KPI and Analytics Dashboard: Real-time performance monitoring and long-term trend analysis for both operations and maintenance teams. • Integrated Alarm and Event Management Module: For real-time system alerts, incident correlation, and SLA tracking. • Flexible Workflow Engine: Enables operators to configure rule-based operational responses without modifying core code. These additional components are integrated into the overall TMS platform in a modular fashion, ensuring full compatibility with the architecture in Figure 3 while allowing room for customization based on SZ’s strategic goals and evolving infrastructure. | Our company proposes a multi-layered, standards-based integration approach to ensure seamless and reliable interfacing between the TMS Control Level and future signalling systems supplied by various manufacturers. Our core integration strategy includes the following technical solutions and protocols: 1. Adoption of the EULYNX SCI-CC Standard: "XXX" TMS is fully compatible with the SCI-CC (System Control Interface – Command and Control) protocol defined by the EULYNX initiative. This is the preferred and most future-proof standard for interfacing TMS with interlocking and ETCS subsystems from multiple vendors. SCI-CC ensures a uniform abstraction layer, simplifying interoperability and integration testing. 2. Use of OPC UA and RESTful APIs: for complementary systems and legacy equipment, "XXX" supports OPC UA (Unified Architecture) and RESTful web services. These protocols allow structured, scalable, and secure data exchange with external systems such as legacy interlockings, SCADA platforms, or diagnostic tools. 3. Middleware for Vendor-Specific Adaptation: where direct SCI-CC support is not feasible (e.g., with older signalling systems), Our company offers a middleware translation layer, using protocol adapters to map vendor-specific formats to normalized interfaces. This ensures backward compatibility without altering core system logic. 4. Message Bus Architecture with Event-Driven Communication: internally, "XXX" uses an event-driven architecture based on message queuing (e.g., "XXX" or "YYY") to handle real-time data synchronization across modules. This decoupled model enhances resilience and simplifies the onboarding of new interfaces. 5. Support for FRMCS-Ready Design: in preparation for future integration with radio-based signalling, "XXX" architecture is aligned with FRMCS (Future Railway Mobile Communication System), ensuring long-term compatibility with GSM-R successors. In summary, our companys integration strategy emphasizes open standards, modularity, and scalability to accommodate diverse signalling systems—ensuring future expansion of the Czech HSL network with minimal disruption or vendor lock-in. | Our approach to adapting the EULYNX SCI-CC specification for the Správa železnic (SZ) High-Speed Lines (HSL) environment is grounded in interoperability, configurability, and compliance with evolving European standards. Our strategy ensures that the TMS can interface seamlessly with a range of signalling technologies while remaining aligned with SZ’s operational and cybersecurity policies. Adaptation Strategy 1. Tailoring SCI-CC Profiles to Czech Infrastructure: we begin by analyzing the existing control and signalling infrastructure at SZ, mapping it against the baseline EULYNX SCI-CC schema. We then co-develop a localized SCI-CC profile that accounts for national operational practices, fail-safes, and data exchange nuances. This approach leverages our experience in adapting SCI-CC in Italy and France, including integration with proprietary interlockings. 2. Collaborative Testing and Validation: Our company recommends establishing a joint validation environment, potentially within the proposed training hall, where interface scenarios can be tested using emulators or pre-integrated IXL simulators. This facilitates faster alignment between TMS and future signalling components during both development and pilot phases. 3. Open Interface Documentation and Version Control: our solution includes fully documented SCI-CC mappings and modular integration logs. We propose maintaining an interface control document (ICD) repository accessible to SZ and third-party signalling vendors, enabling streamlined onboarding and consistent change management. Proposed Use in the Project 1. System-to-IXL Interfacing: SCI-CC will serve as the primary protocol for commanding and monitoring interlocking logic and route control from the TMS Control Level. 2. Safety Layer Communication: Where applicable, SCI-CC will be used to exchange critical safety state data (e.g., route status, lock confirmations, release authorizations). 3. Progressive Rollout: SCI-CC-based connections will be first tested during Milestone 2 (training and simulation) and validated in pilot settings under Milestone 4, allowing adjustments before full-scale deployment. In essence, SCI-CC will be the linchpin for achieving vendor-agnostic signalling integration, which is crucial for future expansion and ensuring a unified command and control environment across Czech HSL corridors. | Yes, our company is fully capable of defining the communication protocol between the TMS Control Level and the Executive Level (RBC, interlocking) in alignment with the architecture described in Figure 2 of Appendix 2 and in close cooperation with Správa železnic. Our company possesses the required technical competence and practical experience to specify, implement, and validate this protocol. Our development teams are deeply familiar with the functional layers of both interlocking and radio block center (RBC) systems, and we have previously implemented such protocols within projects governed by EULYNX, ETCS Level 2, and CENELEC standards. In previous high-speed rail initiatives, we have successfully led the integration of TMS platforms with signalling and RBC infrastructure through collaborative workshops, interface definition sessions, and functional testing sprints—ensuring full alignment between traffic management logic and field-level execution systems. We might propose a joint working group with SZ and signalling vendors to co-develop a well-documented, secure, and standards-aligned communication protocol. This would include: • Command formats for route and traffic instructions • Status feedback loops from interlockings and RBCs • Synchronization with ETCS Level 2 movement authority logic • Real-time performance feedback to the TMS user interface This interface would be designed with flexibility to support multiple signalling vendors, redundancy, and future integration with FRMCS. If SZ considers a new protocol definition unnecessary, due to an existing standardized middleware or procurement strategy, Our company can instead align with any pre-defined interface layer and deliver adapter components as part of the TMS platform to ensure compliance and seamless communication. In summary, we strongly recommend proactive definition of this protocol to guarantee long-term system interoperability, safe operations, and alignment with the 2033 HSL launch timeline. | Integrační strategie společnosti klade důraz na otevřené standardy, modularitu a škálovatelnost, aby bylo možné přizpůsobit se různým signalizačním systémům – zajišťujícím budoucí rozšíření české vysokorychlostní sítě s minimálním narušením nebo závislostí na dodavateli. | Yes, our company guarantees that the "XXX" TMS platform is compatible with signalling systems manufacturers, even without relying on EULYNX-type solutions. Over the past decade, "XXX" has been successfully integrated with a variety of interlocking and signalling systems across different railway environments using both standardized and proprietary protocols. These integrations have been achieved through the use of modular middleware, protocol adapters, and extensive vendor-specific testing. Specifically, nowadays "XXX" TMS is compatible with signalling systems from the following manufacturers: "unnamed companies" Integration has been achieved through legacy and modern interlocking components, using custom interface adapters for command and status exchanges. These integrations were accomplished through customized interface layers, with adaptation to each supplier’s specific protocols and command sets, while preserving system integrity and performance. Our company approach ensures vendor independence and facilitates the seamless evolution of infrastructure, allowing Správa železnic to scale its TMS environment without architectural or contractual lock-in. | If a complete TMS solution were to be developed from the ground up, including all required customizations, integrations with existing systems, hardware commissioning, user training, and system validation, our company estimates a total project duration of approximately 48 to 60 months. This timeframe includes: • Design and specification phase (6–9 months): Joint requirement definition, interface analysis, and architecture validation. • Core system development (12–18 months): Customization of modules including timetable planning, real-time control, and analytics. • Integration with legacy and new signalling systems (6–12 months): Includes development of adapters, testing of EULYNX or custom interfaces, and cybersecurity alignment. • Factory Acceptance Testing (FAT) (3–4 months): Conducted in a pre-production environment. • Site installation and control room integration (6–9 months): Deployment of hardware and configuration at CDP Prague and Přerov. • Pilot operations and fine-tuning (6–8 months): Initial operations on the first HSL section, including operator feedback loops. • Staff training and documentation (ongoing during development and pre-Go-Live) • Final commissioning and Go-Live (aligned with Milestone 4) This timeline reflects full project lifecycle delivery based on Our company’s structured methodology and aligns with the dates envisioned in Appendix 4. Modular rollout and parallel task streams can help optimize phases without compromising quality or regulatory compliance. | Our "XXX" platform is a mature, ready-made Traffic Management System designed to be modular, configurable, and adaptable to national railway environments. If selected as a baseline solution for Správa železnic, it could be rapidly customized to meet Czech HSL requirements through the following adaptation process: Configuration and Localization Strategy 1. Functional Parameterization: "XXX" includes configurable business rules, operational workflows, and user interface settings. These can be tailored to reflect SZ-specific practices, such as train prioritization rules, conflict resolution policies, and station-specific operational procedures—without the need for core code changes. 2. Interface Adaptation: Using "XXX´s" modular interface layer, we can implement adapters for existing SZ systems (e.g., planning tools, interlockings, RBCs) using either standard protocols (e.g., EULYNX SCI-CC, REST, OPC UA) or proprietary ones. These interfaces are documented, versioned, and tested to ensure seamless data exchange. 3. Localization and Language Support: The system can be fully localized into Czech, including all operator workstations, decision support dashboards, and error messages. Multi-language capability also allows parallel support for international staff or cross-border coordination. 4. Training and Simulation Environment: "XXX" includes a simulation module that can be customized to replicate the future HSL topology of the Czech network. This supports early operator familiarization, validation of operational logic, and staff certification. 5. Compliance and Certification: as part of the adaptation process, our company ensures alignment with European and Czech regulatory frameworks, including cybersecurity requirements (NIS2, CZ Act No. 181/2014), safety protocols, and interface standards. By selecting "XXX", SZ would significantly reduce the development timeline and risk profile while retaining the flexibility to shape the system around its national strategy and HSL operational concept. | Our company has carefully reviewed the minimum requirements for TMS as outlined in Appendix 2, paragraph 3, and confirms that all listed requirements are feasible and compatible with the current capabilities of the "XXX" platform. Our experience in designing and deploying traffic management systems for complex rail networks confirms that the functional, technical, and safety expectations defined by Správa železnic are realistic and aligned with industry trends. That said, we would like to offer the following constructive observations: 1. Redundancy and Availability Requirements: We fully support the emphasis on high availability and hot redundancy. We recommend that the specifications explicitly clarify the preferred model (e.g., 1:1 hot standby, n+1 architecture) and whether mirrored operations are required for both CDP Prague and CDP Přerov simultaneously. These details will guide optimal system and network design. 2. Cybersecurity Compliance: The cybersecurity expectations align with EU NIS2 and Czech national legislation. We suggest that future procurement documentation include references to specific security certification frameworks (e.g., ISO/IEC 27001, ISMS audit scope) to streamline supplier alignment. 3. Diagnostic and Monitoring Tools: "XXX" supports proactive diagnostics and SLA monitoring. However, we suggest the specification distinguish between basic event logging and advanced predictive maintenance, which require different levels of system integration and data analytics. 4. Data Ownership and Interoperability: It would be beneficial to clarify the rules surrounding long-term data ownership, especially for logs, operational analytics, and AI-based decision support tools. Ensuring interoperability with future national platforms or EU data corridors would reinforce the system’s value. In conclusion, our company sees no significant difficulty in fulfilling the specified minimum requirements and appreciates the clear structure and realism of the expectations. We remain available to clarify any aspects or provide proof-of-concept demonstrations. | Our company proposes to deliver the entire final TMS product under a single contractual responsibility, ensuring full integration, accountability, and system coherence. However, as is standard in complex infrastructure projects, the solution will include components developed and delivered through specialized partners, particularly for hardware supply, on-site services, and localized training. Breakdown of Responsibility Internally Delivered by Our company: • Development and customization of the "XXX" TMS software platform • Integration with signalling systems (SCI-CC, RBC, IXL) • Operator interfaces, traffic logic, KPI dashboards, and decision support tools • Interface layers to legacy systems, planning tools, and external platforms • Cybersecurity architecture and core system documentation Delivered by our Czech Qualified Partner ICZ (Under our company Oversight): • Supply and installation of server infrastructure and workstation hardware for CDP Prague and CDP Přerov • Local staff training delivery in Czech language (based on our company training materials) • On-site support services and first-line maintenance • Translation and adaptation of manuals, user interfaces, and help systems All third-party contributions will be fully integrated and validated by our company. We assume overall responsibility for system performance, milestone delivery, and regulatory compliance. This ensures that Správa železnic benefits from a unified system while leveraging the best available capabilities from both international and local sources. | Our company has undirect experience integrating Signal Controlled Warning Systems (SCWS), also known as TWS (Track Warning Systems), within live railway operational environments in both EU and non-EU countries. In collaboration with an unnamed infrastructure operator, our company has contributed to the integration of SCWS elements within regional corridors around two big cities, ensuring safe on-track worker operations through automated signal-controlled alerts and operator interfaces. The SCWS modules were integrated into the broader "XXX"-based traffic management framework, demonstrating real-time responsiveness and fail-safe behavior. The SCWS solution was designed with CENELEC compliance, automated field signal interfacing, and configurable warning intervals. These implementations confirm our company´s competence in integrating worker safety mechanisms into live rail infrastructure with operational traffic. | Our company has extensive experience delivering large-scale, mission-critical railway systems, including traffic management, integrated control centers, and signalling interfaces, both in the EU and internationally. We consider a 7-year reference period appropriate and sufficient to assess relevant experience for this type of procurement, as it captures our most significant TMS deployments and system evolution aligned with EULYNX and ETCS integration. <The specific projects listed below have been kept anonymous> | Yes, the "XXX" TMS platform can be supplemented with SCWS-I (Signal Controlled Warning System – Integrated) functionality. Our system architecture is modular and designed to interface with a variety of safety and operational subsystems, including those related to track worker protection. Integration Possibilities "XXX" can interface with SCWS-I through a dedicated Track Control Subsystem (TCS), which manages communication between the traffic management layer and the warning system. This integration enables: • Real-time activation of warning signals based on traffic states • Centralized tracking of maintenance zones and worker presence • Safe coordination between train movements and track access System Requirements and Limitations To ensure seamless SCWS-I integration, the following conditions should be considered: • Interoperable interfaces: SCWS-I must support communication standards such as REST, MQTT, or OPC UA for effective integration. Alternatively, a protocol adapter can be deployed. • Geospatial alignment: The SCWS-I system should share or expose geolocation data (e.g., GPS or track segment mapping) compatible with TMS asset tracking. • Alarm and override logic: If SCWS-I includes active override or emergency stop functions, these need to be formally modeled within "XXX’s" decision support and safety layers to preserve operational integrity. In summary, "XXX" can support SCWS-I integration with needed configuration, provided that the interface specifications and field data are made available during the early design phase. | Based on our experience with modular TMS deployments, including in multi-line environments, the connection of a new High-Speed Line (HSL) section to an operational TMS can typically be completed within 3 to 9 months, depending on complexity, interface availability, and data readiness. Time and Financial Estimates • Timeframe: 3–9 months per section • Effort: Approximately 400–800 man-days depending on signalling integration, data quality, and interface testing • Costs: Estimated at €500,000–€1,000,000 per section, including interface configuration, data ingestion, system testing, and user training This modular extension process benefits from "XXX’s" scalable architecture and configuration-driven design. The system allows new sections to be added with minimal disruption to existing operations, while maintaining centralized oversight. Impact of Data Format Yes, the format and structure of data provided for new HSL sections significantly impact the integration timeline and effort. High-quality, standardized data accelerates configuration, validation, and operational testing. Our company recommends and supports the following data formats: • XML/JSON: Structured data formats ideal for automated parsing and configuration loading • UIC 406 profiles: Standardized for railway operational planning • CSV with metadata schema: Acceptable for tabular inputs (e.g., timetable matrices, asset inventories), provided documentation is clear Early access to properly formatted data allows for parallelization of engineering tasks, reducing the critical path for section onboarding. | Yes, the "XXX" TMS platform is fully capable of interfacing with a TMS from another manufacturer, which is essential for ensuring interoperability on cross-border High-Speed Line (HSL) connections. Our company has already implemented such integration in international corridors where coordinated traffic control between two national systems was required. "XXX" supports multiple communication protocols and interface standards that enable seamless cross-system collaboration, including: • EULYNX SCI-TMS or SCI-CC for standardized TMS-TMS coordination (if supported by both systems) • RESTful APIs for structured data exchange related to train runs, route requests, slot allocation, and conflict resolution • Message brokers (e.g., "XXX", "YYY") for real-time synchronization of traffic states, alarms, and status updates In practice, such TMS-to-TMS integrations involve defining common message structures, shared data semantics, and synchronization rules for traffic planning, handover procedures, and safety contexts. | Our company understands the importance of long-term sustainability, maintainability, and technological independence in the context of national infrastructure systems such as the TMS Control Level. We are therefore open to discussing the provision or licensing of system source code, under clearly defined conditions that ensure both operational continuity for Správa železnic and protection of proprietary innovations. Approach to Source Code Provision 1. Source Code Escrow: our company offers a source code escrow agreement as a standard practice. The code is deposited with a trusted third-party escrow agent and made accessible to Správa železnic under predefined trigger events (e.g., insolvency, contract termination, failure to meet support obligations). 2. Licensing for Internal Use: we are open to granting non-exclusive, non-transferable licenses for the source code, allowing Správa železnic or a designated partner to maintain and further develop the system independently, provided appropriate safeguards are in place. 3. Joint Development Framework: for modules developed specifically for SZ (e.g., Czech-specific adaptations, training interfaces), our company a is willing to negotiate co-ownership or shared IP rights, supporting national control over mission-critical components. Conditions and Concerns 1. Security and Integrity: Any distribution or modification of source code must not compromise system safety, cybersecurity, or third-party interoperability. 2. IP Protection: Core "XXX" modules developed independently by us and used across other clients must remain protected from unauthorized replication or resale. 3. Compliance: Export of source code and software may be subject to EU regulations and must comply with applicable licensing terms. In conclusion, our company is committed to providing Správa železnic with the long-term flexibility it requires, while maintaining a responsible balance between openness and intellectual property stewardship. | Our company is open to discussing the transfer of ownership rights for specific components of the TMS solution, particularly those developed exclusively for Správa železnic under this project. While full transfer of ownership for all "XXX" modules may not be feasible due to their use across multiple railway clients and their proprietary nature, we are prepared to offer a tailored and legally sound framework that provides Správa železnic with substantial autonomy and long-term control. Steps Toward Ownership Transfer or Equivalent Control 1. Modular IP Separation: we can define a clear boundary between: Core "XXX" components (shared IP, under license) and Custom-developed modules for SZ (eligible for full IP transfer) 2. Full Access to Source Code and Documentation: we can provide complete technical documentation, build environments, API definitions, and operational manuals to ensure SZ can maintain and evolve the system independently if desired. 3. Developer Handover and Training: our company might offer a structured knowledge transfer program, including on-site or remote workshops, system architecture deep dives, and guided codebase walkthroughs. This ensures that internal or third-party development teams at SZ can assume responsibility over the system. 4. Licensing with Development Rights: for core "XXX" components, we can offer perpetual licenses with rights to modify, extend, and integrate the code under defined terms, ensuring flexibility without requiring full ownership transfer. 5. Source Code Escrow with Expanded Rights: we are willing to expand escrow agreements to include emergency development rights, enabling SZ or its designated partners to access and evolve the codebase under controlled conditions. Feasibility Yes, this is a feasible requirement for our company, provided the scope is clearly defined and safeguards are implemented to protect shared intellectual property. Our goal is to empower Správa železnic with technological independence while preserving software integrity and long-term maintainability. | Our company recommends that the contract include a support and system development period of at least 7 years following full system commissioning, with the possibility of extending this period up to 10 years through optional tranches or framework extensions. Recommended Timeline 1. Initial support period: 7 years post-Go-Live: includes corrective maintenance, technical support (L2/L3), software updates, cybersecurity patches, and operational monitoring. Covers regular performance audits and minor functional enhancements as needed 2. Optional extension period: Up to 3-5 additional years. May include adaptive maintenance (e.g., integrating new HSL sections), evolving national or EU standards (e.g., FRMCS), and long-term SLA-based support This 7+5 year structure is consistent with best practices in long-term railway system contracts and ensures that Správa železnic receives ongoing system stability, security compliance, and capability evolution without procurement delays or fragmentation. We are open to discussing alternative models based on operational needs or budgetary constraints, including modular support packages for individual subsystems (e.g., TMSNet, KPI dashboards, or SCWS integration). | The lifetime of a Traffic Management System (TMS) is typically influenced by a combination of technical, regulatory, and operational factors. Based on our company experience in maintaining national and regional railway systems, we estimate a typical system lifetime of 15 to 20 years, during which time both technological and functional sustainability must be proactively managed. Technical Factors • Software architecture modularity: Systems built on modular, service-oriented architectures (like "XXX") allow individual components to be updated or replaced without full system overhaul. • Scalability and integration readiness: Lifespan is extended if the TMS can easily interface with evolving signalling systems, communication standards (e.g., FRMCS), and external platforms. • Cybersecurity posture: Long-term viability depends on the ability to adopt emerging security standards and patch vulnerabilities over time. Moral/Functional Factors • Adaptability to new operational concepts: The system must support evolving train control strategies (e.g., ATO, digital dispatching) and performance metrics. • User interface evolution: Changes in operator expectations and human-machine interaction tools may drive upgrades to visualization layers or control logic. • Regulatory compliance: New EU or national mandates (e.g., TAF/TAP-TSI, NIS2) may necessitate functional expansions or audits. Long-Term Support Experience Our company has provided 10–15 years of continuous support for railway systems deployed in Ital. Our contracts typically include: • SLA-based technical support and incident resolution • Scheduled software updates and version migrations • Cybersecurity lifecycle management (e.g., vulnerability scanning, risk assessments) • Periodic functional reviews with client stakeholders Our long-term partnerships with infrastructure managers and regional transport authorities have allowed us to implement proactive maintenance strategies that significantly extend system usability while controlling upgrade costs. | Our company is fully committed to ensuring business continuity and long-term operational resilience for Správa železnic. We propose a well-defined exit strategy designed to guarantee the seamless transfer of system management and operations, even in the event of contract termination or if our company is unable to continue fulfilling its service obligations. Proposed Exit Strategy Components 1. Source Code Escrow with Trigger Clauses: all critical software components—including custom developments—can be placed in escrow with clearly defined release conditions (e.g., vendor insolvency, contractual breach). This ensures immediate access to the source code and build instructions if needed. 2. Knowledge Transfer Plan: a structured handover process will be initiated as part of contract closure, including: a. Comprehensive system documentation (architecture, interfaces, configurations) b. On-site or remote technical workshops for SZ or its designated IT partner c. Transfer of operational procedures and troubleshooting guides d. Walkthroughs of deployment scripts, test environments, and CI/CD pipelines 3. Technical Handover Package: our company will deliver a full technical continuation kit including: a. Perpetual license b. Deployment containers c. Configuration management templates d. Network topology and integration points 5. Fallback Support Engagement (if feasible): in cases of voluntary withdrawal, our company may offer to assist in onboarding a new supplier or provide transitional support for an agreed period. 6. Open Standards and Interface Documentation: "XXX" is built on open, well-documented standards (e.g., REST, OPC UA, SCI-CC). This ensures that future system administrators or developers can interface with the system without dependency on proprietary formats or tools. 7. Third-Party Maintainability: where and if requested, our company can train and certify a local technical partner or Správa železnic’s internal team to ensure continuity of system operations and further development. Continuation of Operations The combination of perpetual licensing, full documentation, and trained internal stakeholders ensures that system operations can continue with no disruption. Operational data, monitoring dashboards, and user-facing components remain under Správa železnic’s control throughout the transition. | Our company proposes an open, modular, and scalable integration framework for connecting the TMS Control Level to future communication and auxiliary systems—including operation applications, CCTV platforms, and passenger information systems. The "XXX" platform is designed around interoperability by default, supporting a wide range of communication protocols and integration standards. Proposed Technical Solutions 1. API-Driven Architecture: "XXX" exposes standardized, secure APIs (REST, GraphQL, and WebSocket) for real-time data exchange with third-party systems. These APIs are documented, versioned, and support asynchronous message handling for scalability. 2. Message Broker / Event Bus: For time-critical or high-volume integration scenarios (e.g., CCTV alerts, operations dashboards), we recommend using event-driven middleware such as "XXX" or "YYY". This ensures decoupling of subsystems and facilitates efficient communication across systems from various manufacturers. 3. Protocol Adapters: For systems that do not support open interfaces, "XXX" includes configurable protocol adapters that convert proprietary data formats into standardized messages. These can be used for legacy CCTV or internal operational platforms. Recommended Standards and Protocols • CCTV and Video Surveillance: "XXX" (for video streaming and storage control) • Passenger Information Systems: "XXX" (General Transit Feed Specification – Real-Time) and "XXX" for structured timetable and disruption info • Operation and SCADA Systems: "XXX" for telemetry and control data; "XXX" for network management • Communication Gateways: SIP and VoIP protocols for integrating dispatch systems and call centers Integration Strategy During implementation, we propose establishing a sandbox environment for testing third-party system connections. This allows vendors and internal teams to verify interface compatibility without impacting live operations. In conclusion, our company´s integration architecture ensures vendor-neutral, resilient, and secure interfacing—empowering Správa železnic to adapt and expand its communication ecosystem over time. | Yes, our company fully confirms that the "XXX" TMS platform and its associated infrastructure components can be delivered in full compliance with the applicable Czech and European cybersecurity regulations, including: • Cyber Security Act (Act No. 181/2014 Coll.) • Cyber Security Decree (Decree No. 82/2018 Coll.) • Directive (EU) 2022/2555 (NIS2 Directive) • Regulation (EU) 2019/881 (EU Cybersecurity Act / ENISA Regulation) Compliance Strategy 1. Risk-Based Design: The system is designed with a security-by-design and security-by-default approach, applying risk management practices consistent with ISO/IEC 27001, NIST CSF, and the Czech NÚKIB guidelines. 2. Secure Physical Infrastructure: our solution includes guidelines and recommendations for: a. Securing cable routes and ICT infrastructure. b. Hardening of distribution cabinets and network endpoints. c. Zoning of server and control rooms in compliance with physical access control standards. 3. Logical and Network Security a. End-to-end encryption using TLS and ECDSA certificates. b. Role-based access controls (RBAC) and secure authentication (e.g., LDAP/AD integration). c. Continuous logging and real-time anomaly detection with support for SIEM integration (e.g., SPLUNK) 4. Audit and Certification Readiness: Our company supports the deployment of "XXX" within environments requiring national certification audits. Our team can assist SZ in preparing compliance documentation and conducting risk assessments aligned with ENISA best practices. 5. Ongoing Security Lifecycle Management a. Regular vulnerability scanning and patch management b. Security incident response procedures (aligned with NIS2) c. Cybersecurity training and awareness programs for SZ operators and system users In summary, our company guarantees that the TMS solution will meet all current and emerging cybersecurity requirements as defined by Czech law and EU directives, ensuring a secure and resilient control environment for high-speed rail operations. | From our company’s perspective, it is fully feasible for the proposed "XXX" TMS system to: 1. Support access control via integration with Active Directory (AD): "XXX" supports integration with LDAP-based identity providers, including Microsoft Active Directory. This allows for centralized user management, role-based access control (RBAC), single sign-on (SSO), and audit logging of user activities. 2. Secure all communication using SSL certificates issued by an internal Certification Authority (CA) that employs the ECDSA algorithm: The platform supports TLS encryption with certificates issued by both public and internal (private) CAs. The use of the ECDSA algorithm is supported and preferred due to its enhanced performance and cryptographic strength. We can configure "XXX" to accept and validate ECDSA-based certificates at both the server and client level. In environments where ECDSA may not be supported by all legacy components, we can offer dual-stack compatibility using RSA + ECDSA hybrid certificates or fallback to RSA for backward compatibility—though ECDSA remains our recommended choice for future-proof security. Our company confirms the full feasibility of implementing centralized access control via AD and secure communications via ECDSA-signed SSL certificates, ensuring robust cybersecurity and compliance with EU and Czech regulations. | From our company’s perspective, it is entirely feasible for the proposed "XXX" TMS system to connect to a central log collection system such as SPLUNK. In fact, centralized log management is a standard feature in our system architecture and is essential for maintaining cybersecurity compliance and operational transparency. Logging Integration Capabilities "XXX" supports multiple mechanisms to forward logs to external systems, including: • Syslog (RFC 5424) – Standard protocol for real-time log forwarding, supported by SPLUNK’s Universal Forwarder. • RESTful API endpoints – "XXX" can push structured log entries via HTTPS to SPLUNK or other SIEM solutions. • File-based export – Log files can be exported in CSV, JSON, or XML format for batch ingestion. • SPLUNK Forwarder Compatibility – Our system is compatible with deployment of SPLUNK Forwarders directly on relevant nodes if required. Log Types Supported • System logs (authentication, access control, service status) • Application logs (traffic operations, route management, exception handling) • Security event logs (firewall events, intrusion alerts, abnormal behavior) There are no technical limitations that would prevent this integration. If SZ uses a different SIEM platform in the future, similar integration methods can be applied with minimal configuration effort. In summary, the "XXX" TMS platform is fully capable of logging to SPLUNK or equivalent platforms and supports real-time or batch-based log ingestion models. | Our company´s ensures high availability of the "XXX" TMS system through a multi-layered redundancy strategy, both at the software and infrastructure levels. This approach is designed to meet the stringent reliability expectations of high-speed rail operations and national critical infrastructure. High Availability Strategy 1. Redundant Control Centers (CDPs): The system can be deployed in a fully hot-redundant configuration between CDP Prague and CDP Přerov. Each site maintains an independent operational instance of the TMS, with real-time data synchronization and failover capabilities. This ensures that if one center becomes unavailable, the other can take over seamlessly with no operational disruption. 2. 1:1 Redundancy at Application and Infrastructure Levels: "XXX" components are deployed using active-active or active-passive clustering, depending on subsystem criticality. Server virtualization, container orchestration (e.g., Kubernetes), and replicated databases ensure zero data loss and high operational continuity. 3. Network and Power Resilience: dual network paths, independent power supplies (UPS + generators), and automated health-check failover logic are standard in our architecture. 4. Monitoring and Self-Healing: integrated health monitoring and alerting systems enable predictive maintenance and automatic restart or migration of failed services. Availability Metrics • Target system availability during HSL operation: ≥ 99.995%: this corresponds to <26 minutes of annual downtime, meeting the high standards required for uninterrupted high-speed traffic management. • Planned maintenance is conducted with zero or near-zero service interruption via rolling updates and session handover between mirrored systems. Proven Performance This availability model is already in use in our company deployments for one european country regional control centers, where we have consistently achieved SLA benchmarks for availability and response time. | To meet the requirement of immediate takeover between workplaces in Prague and Přerov, our company proposes a hot-redundant dual-site configuration where both control centers operate in synchronized, fully operational states. This architecture allows instantaneous failover with no data loss or user disruption in the event of a failure at either site. Proposed Solution: 1:1 Hot Standby Redundancy • Mirrored TMS Instances: each workplace (CDP Prague and CDP Přerov) hosts an independent instance of the "XXX" TMS, with identical configurations and synchronized real-time data. • Live Session Transfer: operator sessions, traffic plans, and route control statuses are continuously replicated between the sites. If one workplace fails, operators at the alternate site can immediately resume control using the latest operational state. • Automatic Failover Mechanism: a high-availability monitor (cluster manager or orchestration layer) constantly checks system health. Upon detecting a critical failure, traffic control responsibility is automatically re-routed to the standby site. • No Central Point of Failure: critical services (e.g., database, middleware, user interface backend) are distributed and replicated across both sites. This ensures that operations can continue from either location without performance degradation. Security and Operator Access • Secure role-based login at both sites • User and workstation failover procedures preconfigured and tested • Seamless coordination with centralized logging and monitoring tools This architecture guarantees that HSL operations can be immediately continued from the alternate workplace, maintaining safety and punctuality even in adverse scenarios. | Our company ensures the fault tolerance of the "XXX" TMS system through a combination of software architecture best practices, redundant hardware deployment, and intelligent system orchestration. The design is intended to isolate faults, recover automatically, and maintain uninterrupted service even under component failure conditions. Fault Tolerance Mechanisms 1. Microservices Architecture: "XXX" is built using a microservices architecture, where each core function (e.g., train scheduling, route control, alarm handling) runs as an independent service. This allows failures to be contained within isolated components without affecting the entire system. 2. Container Orchestration: all services are deployed in containerized environments managed by orchestration platforms. These platforms detect service failures in real time and automatically restart or relocate them to healthy nodes. 3. Redundant and Distributed Components: Databases are deployed in a clustered configuration with automatic replication and failover. Message queues and event buses have high-availability modes to ensure no data is lost or delayed during handover. User interfaces connect to load-balanced backend services to ensure continuity. 4. Health Checks and Circuit Breakers: the system continuously monitors the health of all services using heartbeat signals and performance thresholds. If a service degrades or fails, a circuit breaker pattern reroutes traffic or limits dependency use until recovery. 5. Zero-Downtime Upgrades: system updates and patches are applied using rolling deployments, ensuring no service interruption or operator disconnection. 6. Geographical Redundancy (CDP Prague and CDP Přerov): the dual-site architecture adds another layer of fault tolerance by allowing seamless switch-over between geographically separated control centers. These measures collectively ensure that the "XXX" TMS maintains operation even during hardware faults, software crashes, or localized network disruptions—achieving high fault resilience while meeting the critical demands of high-speed railway operations. | Yes, our company is fully capable of designing and implementing traffic control rooms (CDPs) that are fully aligned with Správa železnic’s Traffic Management Concept as outlined in Appendix 3 and can meet all specified functional requirements in full. Design and Implementation Capabilities 1. Custom Layout and Workflow Optimization: we tailor the physical and functional design of each control room to match SZ’s operational workflow, ensuring efficient collaboration between dispatchers, supervisors, and support staff. Our design team incorporates ergonomic best practices, screen arrangements, acoustic treatments, and redundancy measures. 2. Technology Stack Integration: "XXX" TMS integrates seamlessly with multi-display operator workstations, wallboards, secure network infrastructure, and external systems such as signalling interfaces, planning tools, CCTV feeds, and communication platforms. 3. Role-Based Functional Zones: based on SZ’s concept of layered traffic control (planning, tactical, executive), we configure the system to support role-specific views, workflows, and decision authority. This includes simultaneous multi-user operations and handover protocols. 4. Future-Ready Design: The control room setup supports future enhancements like ATO supervision, AI-based decision support, and coordination with digital twin environments or international traffic control centers. 5. Czech Localization and Regulations Compliance: All user interfaces, documentation, and operator procedures are localized in Czech and compliant with national safety and cybersecurity regulations. Delivery Assurance Our company can deliver the traffic control rooms on a turnkey basis, including civil works coordination, hardware provisioning, system installation, training, and commissioning—backed by our experience designing similar control centers in one European and regional rail hubs. | Based on our experience designing and deploying traffic control centers for high-speed railway networks, the proposed division of workplaces between CDP Prague (TCC Prague) and CDP Přerov (TCC Přerov)—as outlined in the HSL Section Description Tables (Appendix 5)—appears well-structured and operationally sound. Suitability of the Proposed Arrangement • The distribution of responsibilities between the two control centers aligns with the geographical segmentation and operational load of the initial and future HSL phases. • The division supports redundancy and resilience, as both centers are capable of taking over operations in case of disruptions, consistent with high availability requirements. • The architecture encourages parallel traffic handling during peak operations while ensuring a clear delineation of control boundaries, which is key to maintaining safety and efficiency. Suggestions for Optimization • Dynamic Sector Reallocation: we recommend implementing functionality that allows real-time reallocation of control sectors between Prague and Přerov. This enhances flexibility during maintenance, incidents, or future HSL expansions. • Shared Supervisory View: a supervisory layer with visibility over both CDPs would improve coordination during transitions (e.g., train handovers, emergencies). This can be implemented via shared dashboards or inter-center collaboration tools. • Data Analyst or Operations Coordinator Role: introducing a data analyst/support station in each CDP could improve situational awareness, by monitoring KPIs, system health, and incident trends across both centers. The proposed structure is compatible with modern operational practices and provides a solid foundation for scalable traffic management. With the enhancements suggested above, it will support smooth operations and maintain controller efficiency as the HSL network grows. | From our company´s perspective, the current structure of control positions, including the division into line control, traffic control, and electrical control workplaces, aligns well with established operational models used on other high-speed lines in Europe. Strengths of the Current Model • Functional Segmentation: Separating responsibilities among line, traffic, and electrical control supports specialization and focused decision-making, which is essential in high-speed environments where safety and rapid response are critical. • Reduced Cognitive Load: By distributing responsibilities, each operator can concentrate on a specific aspect of control, which reduces error risk and enhances situational awareness. • Coordination-Friendly Layout: When paired with well-designed communication protocols and a shared data environment, this structure enables smooth coordination between roles—particularly during disruptions or maintenance. Our company recommends evaluating whether support roles (e.g., traffic analysts, real-time performance monitors) could be integrated to assist with cross-functional tasks such as disruption analysis or controller relief in high-load periods. The existing division reflects best practices and is well-suited to the Czech HSL context. With optimized tools for coordination and interface design, it can deliver high operational efficiency and safety. | Yes, the current division of sections between CDP Prague and CDP Přerov appears operationally sound and scalable and is generally suitable for ensuring smooth traffic management across the Czech high-speed network as outlined in the HSL Section Description (Appendix 5). Strengths of the Current Division: the segmentation follows a geographic and operational logic, ensuring that each CDP manages a coherent set of HSL corridors with minimal overlap. The structure supports clear delineation of responsibilities, simplifying route planning, coordination, and incident response. Opportunities for Optimization 1. Buffer Zones at Handover Points: implementing flexible “handover buffer zones” at control boundaries can minimize coordination friction. These zones would be visible and optionally controllable by both CDPs during peak traffic or emergencies. 2. Dynamic Control Sector Allocation: introducing the capability to reassign sections dynamically (e.g., based on traffic density or maintenance activity) would enhance resilience and operational agility. This model is used successfully in multi-center setups like those in Italy and Spain. 3. Enhanced Coordination Protocols: while the division is structurally sound, its success depends on synchronization protocols between CDPs. We recommend digital handover dashboards and shared incident resolution workflows to ensure real-time coordination. 4. Predictive Load Balancing: a data-driven approach to predict traffic volume and reallocate sectors based on anticipated congestion could further smooth operations, especially as the network grows. The proposed section division is appropriate for baseline operations. With a few enhancements—such as flexible boundary management, predictive traffic modeling, and digital coordination tools—the setup can be optimized for peak performance and long-term scalability. | Based on our company’s experience with high-speed railway operations in comparable contexts, the currently proposed staffing model for HSL control appears generally adequate for baseline operations. It reflects a well-structured assignment of responsibilities across line control, traffic supervision, and electrical management. Suggested Enhancements 1. Addition of Data Analyst or Operations Coordinator Role: including a dedicated analyst or coordinator can support controllers with real-time performance tracking, disruption impact assessments, and decision-making support. This is particularly beneficial in high-density corridors or during disruption scenarios. 2. Training and Shadowing Period: prior to full operations, a pre-Go-Live simulation and shadowing phase is recommended to validate staffing levels under live-like conditions. 3. Flexibility for Future Roles: as the system evolves (e.g., with ATO, AI-based optimization, or multi-line control), new roles such as “Digital Dispatcher” or “Predictive Maintenance Liaison” may become relevant. The staffing model should be open to future functional expansion. The current staffing structure is a solid foundation. With the addition of operational analytics support and built-in flexibility for future roles, Správa železnic will be well-positioned to ensure effective control of the expanding HSL network. | Yes, the questions from Chapters 1, 2, and 3 are generally comprehensive and well-structured, and they provide a clear view of Správa železnic’s intention to procure a robust, future-ready Traffic Management System (TMS) for the high-speed rail network. The scope, architecture, integration expectations, and operational objectives are all well-communicated. Recommendations for Further Clarification To further enhance alignment between supplier capabilities and project expectations, we suggest that the future procurement documents explicitly define the following: 1. Service Level Agreements (SLAs): clear targets for availability, fault response times, cybersecurity incident handling, and system recovery would allow for more accurate resource and cost planning. 2. Scope Boundaries for Interfaces: clarification of which signalling and communication subsystems will be delivered by SZ versus integrated by the TMS supplier would help in defining interface responsibilities. 3. Modularity and Phased Deployment Expectations: a roadmap of anticipated HSL expansions and how modular rollout is expected to align with procurement tranches would improve planning transparency. 4. Ownership and IP Rights Framework: standardizing expectations around source code access, licensing, escrow possibility and transfer of knowledge would pre-empt negotiation delays during contract finalization. To ensure market alignment and encourage innovation, Our company recommends an optional second round of bilateral technical consultations with shortlisted suppliers before final tender issuance. This could be in the form of: • Technical clarification meetings. • Live Q&A sessions with SZ’s architecture and operations teams. • A shared interface simulation or sandbox environment for pre-validation. These sessions would ensure that technical assumptions are aligned, reduce risk of misinterpretation, and foster a competitive but collaborative procurement process.
10 | XXX | TMS for one specific project is estimated around 80 ME . For RB, we have an OCC and Backup OCC. For RB, ATO is also considered as part of the TMS ==> So I would say around 15-25 ME for this project. | Milestones overall timeline seems reasonable. Commissioning date in 2033 is feasible. However, return of experience and lessons learnt from other TMS project, Milestone 1 duration seems too short. 24 months is a reasonable objective but usually delayed for 1 year or more. Thus, is mainly due to the fact that the contactor shall understand and implement local operational rules, which requires many feedback and agreement with end users Below RB estimated cost distribution 15% Design 45% Equipment 20% Construction / installation 20% Testing | The question is too complex | A typical architecture is to split the network in area of responsibility. Each area is assigned to one Signaller desk during normal operation. Each area is configurable and could be assigned to any signaller desk (managed by a supervisor through access right / credentials). Regarding system architecture, it is recommended to have TMS servers and ATO trackside Servers separated. TMS servers are usually from different types (TMS archiving server, TMS simulation servers, TMS playback servers, TMS servers for operation). TMS server for operation shall be redounded for availability purpose. An interface with Electric system is also usually required to manage train movement in case of powerless section. Interfacing TMS to Interlocking through SCI-CC is recommended, to offer modularity and flexibility on the interface, using an open and known protocol to derisk integration with IXL / RBC. | TMS servers, ATO server and workstation could be part of TMS procurement. Intra-TMS network components shall also be part of the TMS sub-system (telecom cables, switches, …). Furniture (table, desk, chairs, .) could also be provided as part of the TMS procurement. Indeed, TMS supplier will have to conduct Human factor assessment and Ergonomic studies to ensure an optimal comfort for the operators). Layout of the desks in the OCC shall be provided as well. It is recommended to have ATO server separated from TMS server, in case of phasing. Revenue service first without ATO and ATO later could be a phasing strategy | We recommend Eulynx (Baseline 4 R3) SCI-CC for TMS – IXL and TMS-RBC interfaces. It will be based on RasTa protocol which is an open and mature communication protocol. Main benefits from EULYNX are:  Possibility for SZ to control the interface by using an open and standardised protocol,  Neutral interface on which interfacing parties would easily agree,  Possibility to select different suppliers for IXL and TMS reducing integration issues,  Possibility to replace in the future one equipment without changing the full system. As IXL and TMS have different life cycle, they won’t be replaced at a same time period,  Offers a proven and secure communication between TMS and IXL for safety functions, such as Axle Counter Reset,  As a standardised interface, benefit from return of Experience and lessons learnt from EULYNX adopters. | As mentioned above, his interface would be based on SCI-CC from EULYNX baseline 4 R3. This includes Rasta Protocol for the communication layer. EGIS has conducted similar activity for different project, defining from EULYNX SCI-CC the control and indication messages between TMS and CBI (IXL) from 2 different suppliers. The approach to do so was to first capture from existing operation (signallers/regulators use case) what are the needs in terms of control and indication. Then we mapped these needs to EULYNX messages from SCI-CC, to ensure that EULYNX interface will cover the operational needs (bottom-up analysis). In a second time, based on EULYNX SCI-CC we propose to the operator any new features with could benefit to the operation (top-down analysis) | As mentioned above, his interface would be based on SCI-CC from EULYNX baseline 4 R3. This includes Rasta Protocol for the communication layer. Our company has conducted similar activity for different project, defining from EULYNX SCI-CC the control and indication messages between TMS and CBI (IXL) from 2 different suppliers. The approach to do so was to first capture from existing operation (signallers/regulators use case) what are the needs in terms of control and indication. Then we mapped these needs to EULYNX messages from SCI-CC, to ensure that EULYNX interface will cover the operational needs (bottom-up analysis). In a second time, based on EULYNX SCI-CC we propose to the operator any new features with could benefit to the operation (top-down analysis) | EULYNX is designed to be an open and agreed protocol. To mitigate risks, mitigations measures are recommended: EULYNX compliancy homologation by an independent lab and an independent and neutral integrator. Proposed strategy already adopted on our project: • Step 1: Each interfacing system homologate / certify EULYNX compliance in an independent lab • Step 2: In lab, Test Rasta protocol between the 2 systems to interface. This is done using dummy data. This ensures proper communication at a communication layer level • Step 3: In lab, Test the application layer with a “test station”, ensuring the proper functional coverage on a typical station. • Step 4: In lab, test the different line configuration • Step 5: On site: End to end tests A similar strategy can be adopted even in case EULYNX is not adopted (except of course step 1). | To be filled out by product owner | 3 years from notice to proceed to commissioning seems a minimum timeline based on lessons learnt | It is quite unrealistic to consider a ready-made solution without any software development. As mentioned above, TMS is the main interface for operation. User interfaces shall satisfy user requirements, signaller, regulator, and any operational needs. Each operator has its own rules and procedures, different from one country to another, and will therefore require a certain level of development and test. However, the core and generic product and architecture can be reused from a ready-made solution, minimizing software development. | No challenge expected for implementing the requirements listed in Appendix 2 page 4. Automated route, setting, Timetable management, conflict resolution support, priority management are usual functions already deployed in many HSL – ETCS 2 networks. The most challenging requirement are in regards with ATO, as ATO over ETCS is still emerging and under deployment in different projects. | We will integrate all the components from other suppliers, being agnostic, we will ensure the quality of the components chosen in accordance with the critical safety requirements of the railway world We will store the equipment as close as possible to the interventions. To date we have not taken any decisions. | Reference (specific project). | Now, we are currently working on several similar projects. Seven years is a minimum, ideally, we would recommend a period of ten years. | To be filled out by product owner. | There may be one, which is why we are planning the use of a data aggregator that will use rule engines. No, we will conform to your standards. | Few messages to be exchanged (Train describer information), it is usually not a challenge to share operational data with an adjacent TMS. | To be filled out by product owner. | To be filled out by product owner. | To be filled out by product owner. | To be filled out by product owner. | To be filled out by product owner. | It is recommended to use open protocols as far as possible. It is recommended to base the architecture based on Entreprise Service Bus (ESB). ESB performs transformations of data models, handles connectivity, performs message routing, converts communication protocols and potentially manages the composition of multiple requests. The ESB can make these integrations and transformations available as a service interface for reuse by new applications. | To be filled out by product owner. | To be filled out by product owner. | To be filled out by product owner. | It is recommended to have redounded TMS server (hot standby) in each technical room (2 redundant servers in Prague and 2 redundant servers Přerov). It is also recommended to have disaster recovery feature, meaning in case of OCC unavailability (fire, flood, terrorist attack,etc..) it should be possible to recover operation from another workplace. It implies that the TMS servers shall be provided with geo-redundant central servers in the main and backup operating centers configured and the architecture allowing the operation with no interruptions. Any TMS communication interface with adjacent systems through the network shall be redounded as well (Link A and Link B). An availability target for TMS would be: Component (including hardware and software) Inherent Availability Target Target MTBF Server (without redundancy) ≥ 99.50 % ≥ 50,000 hours Workstation ≥ 99.00 % ≥ 40,000 hours | Refer above. It is recommended a Disaster recovery feature as follow: • TMS operation workstations in the Prague control room • TMS operation workstations in the Přerov control room • Main TMS servers in the OCC technical rooms in Prague • Backup TMS servers in the OCC technical rooms in Přerov It will be therefore possible from Prague to take over the operation on south and Noth sections in case of disaster in Přerov. In the other way around, it shall be possible to operate West and East section from Přerov in case of disaster in Prague OCC. It implies that all servers in Prague and Přerov have database of the full line. Workstation in Prague can connect remotely to the servers located in Přerov. Workstations in Přerov can connect remotely to the servers located in Prague. This strategy implies some appropriate training strategy, as operators in Prague and Přerov shall be kept trained on every HSL sections (Noth / South / East / West). | The implementation of a "maintenance assistance system" application that will make it possible to carry out corrective, preventive and predictive maintenance. But also, to monitor the FDMS, MTR, MTBF indicators and we will rely on our SNG product | To be filled out by product owner | Regarding the geographical split between Prague and Přerov, it’s a typical approach for HSL. I some other project, the OCCs for HSL will follow the same approach (North of HSL operated from one location and south part operated from another place, with a recovering capability). It will require, at the boundary between the 2 area, some communication between signallers. | Yes, it corresponds to a typical arrangement. | Task analysis and Human factors assessment to perform to ensure that the signaller is not overloaded. It is premature at this stage. | Task analysis and Human factors assessment to perform to ensure that the signaller is not overloaded. It is premature at this stage. | At this stage of the offer, no.
| Outcome from the preliminary market consultations | The contracting authority obtained an approximate idea of the total costs of implementing the TMS system for high-speed railways in the Czech Republic and took this into account in the estimated contract value. | The contracting authority has ensured that the proposed schedule for the implementation of the TMS project, including individual milestones, is fundamentally realistic and feasible. During the consultation, the individual milestones were discussed and, based on the participants' comments, some of the deadlines were adjusted to reflect the realistic possibilities for their implementation and based on proven practices. | See the PTK output from question 2. | Based on preliminary market consultation, the contracting authority drew inspiration from the solution architectures presented by individual suppliers and thus gained a more accurate and informed picture of the appropriate structure of the TMS control level. Within the architecture design shown in Figure 3, certain functionalities and conceptual approaches presented by suppliers as proven and technically verified were adopted and incorporated. |  | In accordance with the majority consensus, the contracting authority gave preference to the EULYNX solution in the tender. | Based on preliminary market consultation, the contracting authority drew inspiration from the solution architectures presented by individual suppliers and thus gained a more accurate and informed view of the appropriate structure of the TMS control level. Within the architecture design shown in Figure 3, certain functionalities and conceptual approaches presented by suppliers as proven and technically verified were adopted and incorporated. | The contracting authority confirmed that individual TMS suppliers are able to define the necessary communication protocols and interfaces for integration with security devices from different manufacturers well in advance. At the same time, specific technical alternatives and standards commonly used by contractors to ensure interoperability were identified. These findings were taken into account when defining the requirements for TMS compatibility with various types of security devices and when designing the concept for the gradual connection of new HSL sections to the system, regardless of the specific manufacturer of the security technology. | See the preliminary market consultation from question no. 8. | The contracting authority investigated whether contractors were able to guarantee the compatibility of their TMS system with safety devices from at least three different suppliers, even without using a solution such as EULYNX. Contractors confirmed that such compatibility was technically possible, but the preliminary market consultations did not clearly specify the level at which it should be ensured. For this reason, the contracting authority specifies that the required level of compatibility is at the CTC-IL (Centralized Traffic Control – Interlocking) interface, specifically in accordance with the SCI-CC specification. This specification is intended to ensure direct and manufacturer-independent integration of the TMS with various types of safety equipment, and thus the possibility of expanding the system without dependence on a specific supplier of safety technology. | The contracting authority surveyed indicative time frames for the development of the TMS, both in the case of using existing solutions and in the case of a request for the development of a tailor-made system. Based on the responses provided, it was confirmed that the indicative time required for implementation varies significantly depending on the degree of customization, the complexity of integration with external systems, and the availability of data for testing. Suppliers indicated the following indicative time frames: 24-60 months. The number of job positions and their distribution should be assessed and confirmed during the design phase, based on operational scenarios and task analysis | Use of a ready-made TMS solution Based on the responses from suppliers, it was confirmed that it is possible to use a ready-made TMS solution without the need for complete development. Most suppliers offer modular and configurable systems that can be adapted to the requirements of Správa železnic without interfering with the basic code. However, it was also noted that a certain degree of development (particularly in the areas of interfaces, localization, and operational procedures) will always be necessary. | Suppliers have confirmed that all requirements are feasible. For several of them, additional clarification of technical details is needed. | We verified whether the entire final product would be delivered by a single contractor or whether it would contain parts from other suppliers. The suppliers confirmed that the entire TMS system would be delivered by a single contractually responsible contractor. External hardware components would be supplied by specialized suppliers and local partners. They would be provided under the contractor's control and validation. | Most suppliers do not have direct experience with implementing TWS/SCWS in live operations, or confirm that they have solutions developed or in development. | The seven-year period set for the evaluation of reference projects is generally accepted, but it is recommended to allow projects that have reached key milestones (e.g., partial system commissioning, completed integration tests, etc.) to be counted even if they are not yet fully completed. | Suppliers agree in their responses that the integration of the SCWS-I system into their TMS is technically possible and feasible. The tender documentation needs to specify that the integration of SCWS-I will be required as a function (functionality?) that must be implementable, with the technical details to be specified in the implementation phase. | Suppliers agree that the time and financial costs of connecting an additional HSL section to an existing TMS depend mainly on the scope and complexity of the section in question. The format and structure of the data transferred have a direct impact on the efficiency of integration. It is recommended that minimum data format requirements be specified in the tender documentation. | Suppliers agree that technical interconnection of their TMS with another manufacturer's TMS is possible and has already been implemented in practice, particularly in cross-border and multi-system projects. | TMS providers expressly refuse to provide or sell complete source codes on a regular basis in order to protect intellectual property and ensure system integrity. Direct access to source codes cannot therefore be considered a standard or certain option. One supplier explicitly states its openness to providing source codes in the form of a limited license for internal use, possibly with the option of joint development and sharing of rights to modules developed specifically for the contracting authority. | Full transfer of ownership rights to the complete source code of TMS is not standard and is not supported by most vendors due to intellectual property protection and product integrity. | Based on the response, we set the contractual period for TMS support and maintenance at 30 years, which includes: technical support during the launch phase, regular cybersecurity updates, incident resolution, multi-level maintenance, and long-term service with the option of further development as needed. | As part of the preliminary market consultations, we identified factors affecting the service life of the TMS system from a technical and moral point of view, experience with long-term support and maintenance of similar systems, and requirements for the contractual framework for support and development. |  | The aim was to verify the technical readiness of suppliers for integrating the TMS system with various third-party devices, with particular emphasis on the use of open standards, modular and scalable architecture, and minimization of dependence on specific suppliers. | Based on a review of suppliers' responses in preliminary market consultations, the contracting authority drew inspiration from approaches to ensuring the cybersecurity of ICT infrastructure in accordance with applicable legislation. | Most respondents confirmed that the request was valid. | Most respondents confirmed that the request was valid. | Based on the information provided, the input and boundary conditions for calculating availability will be standardized in the tender documentation. | Respondents' inconsistent approach to system failure issues. | Various approaches to ensuring system resilience. | The suppliers agreed that they are capable of performing the specified activities. | The number of job positions and their distribution should be assessed and confirmed during the design and task analysis phase. |  | Most respondents agreed that they did not have sufficient input data to determine the appropriate division of sections. | The tender documentation will require a task analysis and human factors assessment. | The responses indicate market interest in the project and the ability of suppliers to provide solutions. In order to ensure high-quality and comparable bids, it will be necessary to supplement the specific operational scenario, clarify the scope of the interface, specify the required functionalities, and structure the requirements for IT and backup infrastructure. The open dialogue should continue in the next phase of the tender preparation.
Note on AB15: [Komentář ve vlákně] Vaše verze aplikace Excel vám umožňuje číst tento komentář ve vlákně, ale jakékoli jeho úpravy se odeberou, pokud se soubor otevře v novější verzi aplikace Excel. Další informace: https://go.microsoft.com/fwlink/?linkid=870924 Komentář: Bylo cíle dosaženo?